## Hoja1
|  | TELVENT |  |  | Taiwan Power Company Lungmen Nuclear Power Project Units 1 and 2 Contract No. 8749111M03900 | [8 empty] | S: Status 1: Work can proceed 2. Revise and resubmit. Work can proceed subject to incorporation of comments 3. Revise and resubmit. Work can not proceed. 4. For information, no review required.
|  | Index List of Technical Documents / Drawings |  |  | Date : 03/14/2006 |  |  | Doc. Nº 04360.MS039. 8-08001 rev 08
| Limit date (1) | Row# | Plant Unit No. | Document title | Project Document No. | Rev No | S | Planned / Due Date | Action | Ultima Rev Entre Inaben | Fecha Entregado Inabensa | TPC Reply Date | TPC Reply Letter | Telvent Submit Date | Telvent Submit Letter | Remarks | Resp.
|  |  |  | INDEX | [11 empty] | NOTES:
|  | 0 |  | 1. General | [11 empty] | PN = planned to be issued by Telvent
|  | 16 |  | 2. QA Program & Surveillance | [11 empty] | RE = in review process by TPC
|  | #REF! |  | 3. Test and Inspection | [11 empty] | Action: pending action by TPC or Telvent
|  | #REF! |  | 4. Technical Calculations and Reports | [11 empty] | Planned / Due date: planned date to issue the document by Telvent or due date of comments/approval by TPC
|  | #REF! |  | 5. Mechanical | [11 empty] | N/A = not applicable
|  | #REF! |  | 6. Electrical
|  | #REF! |  | 7. Instrumentation and Control
|  | #REF! |  | 8. Arrangement and Interface
|  | #REF! |  | 9. P&IDs
|  | #REF! |  | 10. Equipment Lists and Data Sheets
|  | #REF! |  | 11. Trasnportation, Storage and Installation
|  | #REF! |  | 12. Operation and Maintenance
|  | #REF! |  | 13. Manufacter´s Instructions and Technical Information
|  | 0 |  | 1. General
|  | 1 | Unit 1/2 | Index List of Technical Documents / Drawings Unit 1 and Unit 2 | 04360.MS039. 8-08001 | 0 | 2 |  |  |  |  | 2002-11-04 | SWT-SAI-0015 | 10/23/02 | SAI-SWT-0004 |  | JGG
1 | 1 | 2 |  |  | 04360.MS039. 8-08001 | 1 | 4 | [6 empty] | 01/17/03 | email
2 | 2 | 3 |  |  | 04360.MS039. 8-08001 | 2 | 4 | [6 empty] | 04/04/03 | email
|  | 4 |  |  | 04360.MS039. 8-08001 | 3 | 4 | [6 empty] | 12/10/04 | SAI-SWT-0328
|  | 5 |  |  | 04360.MS039. 8-08001 | 4 | 4 |  |  |  |  | 06/09/05 | SWT-SAI-0256 | 2005-05-06 | SAI-SWT-0349 | The rev 4 (Summary) has been sent to TPC/S&W attached in document 04360.MS039. 7-08600 rev 0
|  | 6 |  |  | 04360.MS039. 8-08001 | 5 | 4 | [6 empty] | 08/17/05 | email
|  | 7 |  |  | 04360.MS039. 8-08001 | 6 | 4 |  |  |  |  | 2005-12-16 | SWT-SAI-0278 | 10/24/05 | SAI-SWT-0370 | The rev 6 (Summary) has been sent to TPC/S&W attached in document 04360.MS039. 7-08600 rev 1
|  | 8 |  |  | 04360.MS039. 8-08001 | 7 | 4 | [6 empty] | 2006-03-03 | N/A | The rev 7 was reviewed during Factory Acceptence Tests
|  | 9 |  |  | 04360.MS039. 8-08001 | 8 | 4 | [6 empty] | 03/24/06 | SAI-SWT-0390 | The rev 8 (Summary) has been sent to TPC/S&W attached in document 04360.MS039. 7-08600 rev 2
3 | 3 | 10
4 | 4 | 11 | Unit 1/2 | Project Schedule | 04360.MS039. 8-08002 | 0 | 2 |  |  |  |  | 11/25/02 | SWT-SAI-0019 | 11/06/02 | SAI-SWT-0007 |  | JBG/JCL
5 | 5 | 12 |  |  | 04360.MS039. 8-08002 | 1 | 1 |  |  |  |  | 01/02/03 | SWT-SAI-0023 | 11/28/02 | SAI-SWT-0010
6 | 6 | 13
7 | 7 | 14 | Unit 1/2 | Final List of Documents for Remote Sampling Cooler Panels and Analyzer Panels for Units 1 and 2 | 04360.MS039. 8-08010 | 0 | 4 | [8 empty] | Included in QA Record Package of First Delivery of panels
8 | 8 | 15
9 | 9 | 16 |  | 2. QA Program & Surveillance
10 | 10 | 17 | Unit 1/2 | Quality Assurance Program | 04360.MS039. 4-00001 | 0 | 2 |  |  |  |  | 11/12/02 11/20/02 | SWT-SAI-0016 SWT-SAI-0018 | 09/20/02 | SAI-TPC-0008 |  | JBG/JCL
11 | 11 | 18 |  |  | 04360.MS039. 4-00001 | 1 | 1 |  |  |  |  | 02/26/03 | SWT-SAI-0029 | 02/04/03 | SAI-TPC-0025
12 | 12 | 19 |  |  | 04360.MS039. 4-00001 | 2 | 1 |  |  |  |  | 05/26/03 | SWT-SAI-0057 | 05/14/03 06/10/03 | SAI-TPC-0029 SAI-TPC-0031
13 | 13 | 20
14 | 14 | 21 | Unit 1/2 | Quality Management Manual | SA-ED-4360-MGC-01 | 0 | 2 |  |  |  |  | 11/12/02 11/20/02 02/26/03 | SWT-SAI-0016 SWT-SAI-0018 SWT-SAI-0029 | 10/17/02 11/14/02 02/04/03 | SAI-TPC-0014 SAI-SWT-0009 SAI-TPC-0025 |  | JBG/JCL
15 | 15 | 22 |  |  | SA-ED-4360-MGC-01 | 1 | 1 |  |  |  |  | 05/26/03 | SWT-SAI-0057 | 05/14/03 06/10/03 | SAI-TPC-0029 SAI-TPC-0031
Note on I3: SEJSGG: Limit es la fecha limite de la accion (planned date o 1 mes despues del envio a TPC o due date despues recibir comentario de TPC ) Color rojo es limite excedido por TPC o por Sainco. Color morado es limite excedido por TPC y carta reclamacion enviada
Note on J3: JSGG: nombre SAINCO/TPC del que tenga que hacer la siguiente acción (revisar documento, contestar algo, enviar aprobacio firmada, etc..) (x) significa pendiente enviar paper copies Color amarillo pendiente de Sainco Color verde pendiente de TPC
Note on N3: JSGG: se incluyen las referencias de faxes/cartas de S&W-TPC que incluyan comentarios y/o las aprobaciones
Note on Q3: JSGG: se incluyen las cartas de comentarios y de envio de documentos de Sainco a S&W-TPC y los faxes de aprobacion, asi como cualquier observacion.

## Hoja2
NO APLICA
|  | 1 | Unit 1/2 | Software Quality Assurance Plan | 04360.MS039. 4.00004 | 0 | RE | 2004-11-22 | TPC |  |  |  |  | 11/22/04 | SAI-SWT-0326 | Telvent sent rev 0 by letter SAI-SWT-0326 of 11/22/04 | JGG
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! | Unit 1/2 | Project Schedule | 04360.MS039. 8-08002 | 0 | 2 |  |  |  |  | 11/25/02 | SWT-SAI-0019 | 11/06/02 | SAI-SWT-0007 |  | JBG/JCL
#REF! | #REF! | #REF! |  |  | 04360.MS039. 8-08002 | 1 | 1 |  |  |  |  | 01/02/03 | SWT-SAI-0023 | 11/28/02 | SAI-SWT-0010
1 | 1 | 1
|  | #REF! | Unit 1 | Equipment Layout Drawing - Control & Recorder Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-12008 | 0 | 2 |  |  | 1900-01-01 | 23/04/04 | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129 | Sainco sent letter SAI-SWT-0155 0f 9/11/03 | JBG/JCL
[5 empty] | 04360.MS039. 5-12008 | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/03/03 | SAI-SWT-0177
[5 empty] | 04360.MS039. 5-12008 | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/23/04 | SAI-SWT-0240
|  | #REF! | Unit 2 | Equipment Layout Drawing - Sample Conditioning Rack of Turbine Sampling System Unit 1 | 04360.MS039. 5-12004 | 0 | 2 |  |  | 3 | 23/04/04 | 06/19/03 | SWT-SAI-0072 | 05/15/03 | SAI-SWT-0058 |  | JBG/JCL
[5 empty] | 04360.MS039. 5-12004 | 1 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 0f 9/11/03.
[5 empty] | 04360.MS039. 5-12004 | 2 | 2 |  |  |  |  | 2004-10-02 | SWT-SAI-0157 | 11/26/03 | SAI-SWT-0193
[5 empty] | 04360.MS039. 5-12004 | 3 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/23/04 | SAI-SWT-0247
1 | 1 | 1 | Unit 1 | Dimensioned Outline Drawing - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360.MS039. 5-12001 | 0 | 2 |  |  |  |  | 1/24/03 | SWT-SAI-0025 | 01/08/03 | SAI-SWT-0011 |  | JBG/JCL
2 | 2 | 2 |  |  | 04360.MS039. 5-12001 | 1 | 2 |  |  |  |  | 2/18/03 | SWT-SAI-0027 | 02/04/03 | SAI-SWT-0016
3 | 3 | 3 |  |  | 04360.MS039. 5-12001 | 2 | 2 |  |  |  |  | 05/21/03 | SWT-SAI-0054 | 04/10/03 | SAI-SWT-0033
4 | 4 | 4 |  |  | 04360.MS039. 5-12001 | 3 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 0f 9/11/03.
5 | 5 | 5 |  |  | 04360.MS039. 5-12001 | 4 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/09/04 | SAI-SWT-0231
6 | 6 | 6
|  | 6 | Unit 1 | Dimensioned Outline Drawing - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12103 | 0 | 3 |  |  | 5 | 23/04/04 | 03/20/03 | SWT-SAI-0036 | 01/27/03 | SAI-SWT-0014
[5 empty] | 04360.MS039. 5-12103 | 1 | 2 |  |  |  |  | 05/30/03 | SWT-SAI-0059 | 05/09/03 | SAI-SWT-0051
[5 empty] | 04360.MS039. 5-12103 | 2 | 3 |  |  |  |  | 07/03/03 | SWT-SAI-0085 | 06/18/03 | SAI-SWT-0080 | Sainco sent letter SAI-SWT-0155 0f 9/11/03
[5 empty] | 04360.MS039. 5-12103 | 3 | 3 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141
[5 empty] | 04360.MS039. 5-12103 | 4 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/28/03 | SAI-SWT-0194
[5 empty] | 04360.MS039. 5-12103 | 5 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/12/04 | SAI-SWT-0249
1 | 1 | 1 | Unit 1 | Equipment Layout Drawing - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360.MS039. 5-12002 | 0 | 2 |  |  | 4 | 23/04/04 | 03/20/03 | SWT-SAI-0036 | 01/27/03 | SAI-SWT-0014 |  | JBG/JCL
|  | 2 |  |  | 04360.MS039. 5-12002 | 1 | 2 |  |  |  |  | 05/19/03 | SWT-SAI-0053 | 04/23/03 | SAI-SWT-0037
|  | 3 |  |  | 04360.MS039. 5-12002 | 2 | 2 |  |  |  |  | 08/25/03 | SWT-SAI-0092 | 06/4/03 | SAI-SWT-0072
|  | 4 |  |  | 04360.MS039. 5-12002 | 3 | 2 |  |  |  |  | 10/08/03 | SWT-SAI-0122 | 08/11/03 | SAI-SWT-0143 | Sainco sent letter SAI-SWT-0151 of 8/8/03.
|  | 5 |  |  | 04360.MS039. 5-12002 | 4 | 2 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/09/04 | SAI-SWT-0231
|  | 6 |  |  | 04360.MS039. 5-12002 | 5 | 1 |  |  |  |  | 07/21/04 | SWT-SAI-0222 | 05/19/04 | SAI-SWT-0275
|  | 7 |  |  | 04360.MS039. 5-12002 | 6 | 4 | [6 empty] | 09/29/04 | SAI-SWT-0299
|  | 8 |  |  | 04360.MS039. 5-12002 | 7 | 4 | [6 empty] | 11/23/04 | SAI-SWT-0327
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF! | Unit 1/2 | QA Record List
|  | #REF! |  |  | 04360.MS039. 8-00005 | 1 | 1 |  |  |  |  | 10/28/04 11/12/04 | SWT-SAI-0240 email by G. Hsi | 10/18/04 | SAI-SWT-0316
#REF!
|  | #REF! | Unit 1/2 | Quality Assurance Record Package for Remote Sampling Cooler Panels and Analyzer Panels of Units 1 and 2 | N/A Project Docum. No. | N/A |  | 12/18/04 | TPC |  |  |  |  | 11/18/04 | SAI-TPC-0044
#REF!
|  | #REF! | Unit 1/2 | Quality Assurance Record Package for Sample Conditioning Racks, Chiller Equipment Panels, Control and Recorder Panels and Spare Parts for Unit 1 and 2 | N/A Project Docum. No. | N/A | PN | See remarks | Telvent | [6 empty] | Telvent will send this documentation to TPC before delivery of the affected equipment
#REF!
|  | #REF! | Unit 1/2 | Software Quality Assurance Plan | 04360.MS039. 4.00004 | 0 | RE | 2004-11-22 | TPC |  |  |  |  | 11/22/04 | SAI-SWT-0326 | Telvent sent rev 0 by letter SAI-SWT-0326 of 11/22/04 | JGG
#REF!
|  | #REF! |  | 3. Detail Design - Mechanical
1 | 1 | #REF!
2 | 2 | #REF! | Unit 1 | Dimensioned Outline Drawing - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360.MS039. 5-12001 | 0 | 2 |  |  |  |  | 1/24/03 | SWT-SAI-0025 | 01/08/03 | SAI-SWT-0011 |  | JBG/JCL
3 | 3 | #REF! |  |  | 04360.MS039. 5-12001 | 1 | 2 |  |  |  |  | 2/18/03 | SWT-SAI-0027 | 02/04/03 | SAI-SWT-0016
4 | 4 | #REF! |  |  | 04360.MS039. 5-12001 | 2 | 2 |  |  |  |  | 05/21/03 | SWT-SAI-0054 | 04/10/03 | SAI-SWT-0033
5 | 5 | #REF! |  |  | 04360.MS039. 5-12001 | 3 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 0f 9/11/03.
6 | 6 | #REF! |  |  | 04360.MS039. 5-12001 | 4 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/09/04 | SAI-SWT-0231
7 | 7 | #REF!
8 | 8 | #REF! | Unit 2 | Dimensioned Outline Drawing - Remote Sampling Cooling Panels of Turbine Sampling System Unit 2 | 04360.MS039. 5-22001 | 0 | 4 | [6 empty] | 09/29/04 | SAI-SWT-0299 |  | JBG/JCL
|  | #REF! |  |  |  | 7
9 | 9 | #REF! | Unit 1 | Equipment Layout Drawing - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360.MS039. 5-12002 | 0 | 2 |  |  | 4 | 23/04/04 | 03/20/03 | SWT-SAI-0036 | 01/27/03 | SAI-SWT-0014 |  | JBG/JCL
|  | #REF! |  |  | 04360.MS039. 5-12002 | 1 | 2 |  |  |  |  | 05/19/03 | SWT-SAI-0053 | 04/23/03 | SAI-SWT-0037
|  | #REF! |  |  | 04360.MS039. 5-12002 | 2 | 2 |  |  |  |  | 08/25/03 | SWT-SAI-0092 | 06/4/03 | SAI-SWT-0072
|  | #REF! |  |  | 04360.MS039. 5-12002 | 3 | 2 |  |  |  |  | 10/08/03 | SWT-SAI-0122 | 08/11/03 | SAI-SWT-0143 | Sainco sent letter SAI-SWT-0151 of 8/8/03.
|  | #REF! |  |  | 04360.MS039. 5-12002 | 4 | 2 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/09/04 | SAI-SWT-0231
|  | #REF! |  |  | 04360.MS039. 5-12002 | 5 | 1 |  |  |  |  | 07/21/04 | SWT-SAI-0222 | 05/19/04 | SAI-SWT-0275
|  | #REF! |  |  | 04360.MS039. 5-12002 | 6 | 4 | [6 empty] | 09/29/04 | SAI-SWT-0299
|  | #REF! |  |  | 04360.MS039. 5-12002 | 7 | 4 | [6 empty] | 11/23/04 | SAI-SWT-0327
#REF!
|  | #REF! | Unit 2 | Equipment Layout Drawing - Remote Sampling Cooling Panels of Turbine Sampling System Unit 2 | 04360.MS039. 5-22002 | 0 | 4 | [6 empty] | 09/29/0 | SAI-SWT-0299 |  | JBG/JCL
[5 empty] | 04360.MS039. 5-22002 | 1 | 4 | [6 empty] | 11/23/04 | SAI-SWT-0327
|  | #REF! | Unit 1/2 | Manufacturing Details - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360.MS039. 5-12602 | 0 | See remarks | [8 empty] | This is a internal Telvent drawing (not sent to TPC/S&W) | JBG/JCL
|  | #REF! | Unit 1 | Dimensioned Outline Drawing - Sample Conditioning Rack of Turbine Sampling System Unit 1 | 04360.MS039. 5-12003 | 0 | 2 |  |  | 4 | 23/04/04 | 01/30/03 | SWT-SAI-0026 | 01/15/03 | SAI-SWT-0012 |  | JBG/JCL
[5 empty] | 04360.MS039. 5-12003 | 1 | 2 |  |  |  |  | 05/21/03 | SWT-SAI-0054 | 04/10/03 | SAI-SWT-0033
[5 empty] | 04360.MS039. 5-12003 | 2 | 2 |  |  |  |  | 10/28/03 | SWT-SAI-0129 | 08/01/03 | SAI-SWT-0132
[5 empty] | 04360.MS039. 5-12003 | 3 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/26/03 | SAI-SWT-0193
[5 empty] | 04360.MS039. 5-12003 | 4 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/23/04 | SAI-SWT-0247
|  | #REF! | Unit 2 | Dimensioned Outline Drawing - Sample Conditioning Rack of Turbine Sampling System Unit 2 | 04360.MS039. 5-22003 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment Layout Drawing - Sample Conditioning Rack of Turbine Sampling System Unit 1 | 04360.MS039. 5-12004 | 0 | 2 |  |  | 3 | 23/04/04 | 06/19/03 | SWT-SAI-0072 | 05/15/03 | SAI-SWT-0058 |  | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 0f 9/11/03.
[6 empty] | 2 | 2 |  |  |  |  | 2004-10-02 | SWT-SAI-0157 | 11/26/03 | SAI-SWT-0193
[6 empty] | 3 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/23/04 | SAI-SWT-0247
|  | #REF! | Unit 2 | Equipment Layout Drawing - Sample Conditioning Rack of Turbine Sampling System Unit 2 | 04360.MS039. 5-22004 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Dimensioned Outline Drawing - Control & Recorder Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-12007 | 0 | 2 |  |  | 3 | 23/04/04 | 03/20/03 | SWT-SAI-0036 | 01/27/03 | SAI-SWT-0014 |  | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 05/19/03 | SWT-SAI-0053 | 04/23/03 | SAI-SWT-0037
[6 empty] | 2 | 2 |  |  |  |  | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129 | Sainco sent letter SAI-SWT-0155 0f 9/11/03
[6 empty] | 3 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/25/04 | SAI-SWT-0242
|  | #REF! | Unit 2 | Dimensioned Outline Drawing - Control & Recorder Panel of Turbine Sampling System Unit 2 | 04360.MS039. 5-22007 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment Layout Drawing - Control & Recorder Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-12008 | 0 | 2 |  |  | 1900-01-01 | 23/04/04 | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129 | Sainco sent letter SAI-SWT-0155 0f 9/11/03 | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/03/03 | SAI-SWT-0177
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/23/04 | SAI-SWT-0240
|  | #REF! | Unit 2 | Equipment Layout Drawing - Control & Recorder Panel of Turbine Sampling System Unit 2 | 04360.MS039. 5-22008 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment and Dimensioned Layout Drawing - Chiller Equipment Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-12009 | 0 | 2 |  |  | 1900-01-01 | 23/04/04 | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129 | Sainco sent letter SAI-SWT-0155 0f 9/11/03. | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/26/03 | SAI-SWT-0193
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/02/04 | SAI-SWT-0246
|  | #REF! | Unit 2 | Equipment and Dimensioned Layout Drawing - Chiller Equipment of Turbine Sampling System Unit 2 | 04360.MS039. 5-22009 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Dimensioned Outline Drawing – Analyzer Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-12010 | 0 | 1 |  |  | 1899-12-31 | 23/04/04 | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129 | Sainco sent letter SAI-SWT-0155 0f 9/11/03 | GGT
[6 empty] | 1 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/25/04 | SAI-SWT-0242
|  | #REF! | Unit 2 | Dimensioned Outline Drawing – Analyzer Panel of Turbine Sampling System Unit 2 | 04360.MS039. 5-22010 | 0 | 4 | [6 empty] | 10/07/04 | SAI-SWT-0306 |  | GGT
|  | #REF! | Unit 1 | Equipment Layout Drawing – Analyzer Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-12011 | 0 | 2 |  |  | 2 | 23/04/04 | 10/28/03 | SWT-SAI-0129 | 08/01/03 | SAI-SWT-0132 | Sainco sent letter SAI-SWT-0155 of 9/11/03 | GGT
[6 empty] | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/21/03 | SAI-SWT-0189
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/23/04 | SAI-SWT-0240
[6 empty] | 3 | 4 | [6 empty] | 10/10/04 | SAI-SWT-0310
|  | #REF! | Unit 2 | Equipment Layout Drawing – Analyzer Panel of Turbine Sampling System Unit 2 | 04360.MS039. 5-22011 | 0 | 4 | [6 empty] | 11/23/04 | SAI-SWT-0327 |  | GGT
|  | #REF! | Unit 1 | Dimensioned Outline Drawing - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12103 | 0 | 3 |  |  | 5 | 23/04/04 | 03/20/03 | SWT-SAI-0036 | 01/27/03 | SAI-SWT-0014
[6 empty] | 1 | 2 |  |  |  |  | 05/30/03 | SWT-SAI-0059 | 05/09/03 | SAI-SWT-0051
[6 empty] | 2 | 3 |  |  |  |  | 07/03/03 | SWT-SAI-0085 | 06/18/03 | SAI-SWT-0080 | Sainco sent letter SAI-SWT-0155 0f 9/11/03
[6 empty] | 3 | 3 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141
[6 empty] | 4 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/28/03 | SAI-SWT-0194
[6 empty] | 5 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/12/04 | SAI-SWT-0249
|  | #REF! | Unit 2 | Dimensioned Outline Drawing - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22103 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment Layout Drawing - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12104 | 0 | 3 |  |  | 3 | 23/04/04 | 06/25/03 | SWT-SAI-0075 | 06/06/03 | SAI-SWT-0074 | Sainco sent letter SAI-SWT-0155 0f 9/11/03
[6 empty] | 1 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141
[6 empty] | 2 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/28/03 | SAI-SWT-0194
[6 empty] | 3 | 2 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/12/04 | SAI-SWT-0249
[6 empty] | 4 | 1 |  |  |  |  | 07/21/04 | SWT-SAI-0222 | 05/19/04. | SAI-SWT-0275
|  | #REF! | Unit 2 | Equipment Layout Drawing - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22104 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Dimensioned Outline Drawing - Control & Recorder Panel of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12107 | 0 | 2 |  |  | 3 | 23/04/04 | 03/20/03 | SWT-SAI-0036 | 01/27/03 | SAI-SWT-0014
[6 empty] | 1 | 2 |  |  |  |  | 05/30/03 | SWT-SAI-0059 | 05/09/03 | SAI-SWT-0051 | Sainco sent letter SAI-SWT-0155 0f 9/11/03
[6 empty] | 2 | 1 |  |  |  |  | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129
[6 empty] | 3 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/25/04 | SAI-SWT-0242
|  | #REF! | Unit 2 | Dimensioned Outline Drawing - Control & Recorder Panel of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22107 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment Layout Drawing - Control & Recorder Panel of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12108 | 0 | 2 |  |  | 1900-01-01 | 23/04/04 | 10/28/03 | SWT-SAI-0129 | 08/01/03 | SAI-SWT-0132 | Sainco sent letter SAI-SWT-0155 0f 9/11/03 | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/24/03. | SAI-SWT-0190
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/23/04 | SAI-SWT-0240
|  | #REF! | Unit 2 | Equipment Layout Drawing - Control & Recorder Panel of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22108 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment and Dimensioned Layout Drawing - Chiller Equipment Panel of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12109 | 0 | 2 |  |  | 1900-01-01 | 23/04/04 | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 12/03/03 | SAI-SWT-0196
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/02/04 | SAI-SWT-0246
|  | #REF! | Unit 2 | Equipment and Dimensioned Layout Drawing - Chiller Equipment of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22109 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Dimensioned Outline Drawing – Analyzer Panel of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12110 | 0 |  |  |  | 1900-01-01 | 23/04/04 | 10/28/03 | SWT-SAI-0129 | 08/01/03 | SAI-SWT-0132 | Sainco sent letter SAI-SWT-0155 of 9/11/03. | GGT
[6 empty] | 1 | [5 empty] | 02/10/04 | SWT-SAI-0157 | 11/21/03 | SAI-SWT-0189
[6 empty] | 2 | [5 empty] | 04/27/04 | SWT-SAI-0207 | 02/25/04 | SAI-SWT-0242
|  | #REF! | Unit 2 | Dimensioned Outline Drawing – Analyzer Panel of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22110 | 0 | 4 | [6 empty] | 38267 | SAI-SWT-0306 |  | GGT
|  | #REF! | Unit 1 | Equipment Layout Drawing – Analyzer Panel of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-12111 | 0 | 2 |  |  | 2 | 23/04/04 | 10/28/03 | SWT-SAI-0129 | 08/01/03 | SAI-SWT-0132 | Sainco sent letter SAI-SWT-0155 of 9/11/03. | GGT
[6 empty] | 1 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/24/03 | SAI-SWT-0190
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/2/04 | SAI-SWT-0247
[6 empty] | 3 | 4 | [6 empty] | 10/11/04 | SAI-SWT-0310
[6 empty] | 4 | 4 | [6 empty] | 11/23/04 | SAI-SWT-0327
|  | #REF! | Unit 2 | Equipment Layout Drawing – Analyzer Panel of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-22111 | 0 | 4 | [6 empty] | 11/23/04 | SAI-SWT-0327 |  | GGT
|  | #REF! | Unit 1 | Dimensioned Outline Drawing - Sample Conditioning Rack of Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-12203 | 0 | 2 |  |  | 3 | 23/04/04 | 06/19/03 | SWT-SAI-0072 | 05/15/03 | SAI-SWT-0058 |  | JBG/JCL
[6 empty] | 1 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 of 9/11/03.
[6 empty] | 2 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 11/21/03 | SAI-SWT-0189
[6 empty] | 3 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/12/04 | SAI-SWT-0249
|  | #REF! | Unit 2 | Dimensioned Outline Drawing - Sample Conditioning Rack of Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-22203 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! | Unit 1 | Equipment Layout Drawing - Sample Conditioning Rack of Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-12204 | 0 | 3 |  |  | 3 | 23/04/04 | 06/25/03 | SWT-SAI-0076 | 06/11/03 | SAI-SWT-0077
[6 empty] | 1 | 2 |  |  |  |  | 10/29/03 | SWT-SAI-0130 | 08/08/03 | SAI-SWT-0141 | Sainco sent letter SAI-SWT-0155 of 9/11/03.
[6 empty] | 2 | 2 |  |  |  |  | 02/10/04 | SWT-SAI-0157 | 12/03/03 | SAI-SWT-0196
[6 empty] | 3 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 03/17/04 | SAI-SWT-0251
|  | #REF! | Unit 2 | Equipment Layout Drawing - Sample Conditioning Rack of Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-22204 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
[12 empty] | 05/21/03 | SWT-SAI-0054 |  |  | Sainco sent rev 0 by email of 4/3/03 and letter SAI-SWT-0033 of 04/10/03. Sainco sent rev 1 by email of 08/01/03 and letter SAI-SWT-0129 of 07/31/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 2 by letter SAI-SWT-0242 of 02/25/04.
|  | #REF! | Unit 1 | Dimensioned Outline Drawing - Control & Recorder Panel of Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-12207 | 0 | 2 |  |  | 1900-01-01 | 23/04/04 | 05/21/03 | SWT-SAI-0054 | 04/10/03. | SAI-SWT-0033
[6 empty] | 1 | 1 |  |  |  |  | 10/08/03 | SWT-SAI-0122 | 07/31/03 | SAI-SWT-0129 | Sainco sent letter SAI-SWT-0155 of 9/11/03.
[6 empty] | 2 | 1 |  |  |  |  | 04/27/04 | SWT-SAI-0207 | 02/25/04 | SAI-SWT-0242
|  | #REF! | Unit 2 | Dimensioned Outline Drawing - Control & Recorder Panel of Auxiliary Boiler Sampling yistem Unit 2 | 04360.MS039. 5-22207 | 0 | PN | 2004-12-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Control & Recorder Panel of Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-12208 | 2 | CC |  |  | 2 | 23/04/04 | 10/28/03 02/10/04 04/27/04 | SWT-SAI-0129 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/01/03 and letter SAI-SWT-0132 of 08/01/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 1 by letter SAI-SWT-0190 of 11/24/03. Telvent sent rev 2 by letter SAI-SWT-0240 of 2/23/04. | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Control & Recorder Panel of Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-22208 | 0 | PN | Final panel | Telvent | [7 empty] | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing – Analyzer Panel of Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-12210 | 2 | CC |  |  | 2 | 23/04/04 | 10/28/03 02/10/04 04/27/04 | SWT-SAI-0129 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/01/03 and letter SAI-SWT-0132 of 08/01/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0189 of 11/21/03. Telvent sent rev 2 by letter SAI-SWT-0242 of 02/25/04.
|  | #REF! |  | Dimensioned Outline Drawing – Analyzer Panel of Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-22210 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04.
|  | #REF! |  | Equipment Layout Drawing – Analyzer Panel of Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-12211 | 3 | CC |  |  | 2 | 23/04/04 | 10/29/03 02/10/04 04/27/04 | SWT-SAI-0130 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/08/03 and letter SAI-SWT-0141 of 08/08/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0189 of 11/21/03. Sainco sent rev 2 by letter SAI-SWT-0247 of 3/23/04. Telvent sent rev 3 by letter SAI-SWT-0310 of 10/10/04.
|  | #REF! |  | Equipment Layout Drawing – Analyzer Panel of Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-22211 | 0 | CC | [8 empty] | Telvent sent rev 0 letter SAI-SWT-0327 of 11/23/04.
|  | #REF! |  | Cross Sectional Drawing - Control & Recorder Panel of Auxiliary Boiler Sampling System Unit 1 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Cross Sectional Drawing - Control & Recorder Panel of Auxiliary Boiler Sampling System Unit 2 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing - Sample Conditioning Rack of Condenser Sampling System Unit 1 | 04360.MS039. 5-12303 | 3 | CC |  |  | 3 | 23/04/04 | 05/30/03 08/21/03 02/10/04 04/27/04 | SWT-SAI-0059 SWT-SAI-0091 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 04/11/03 and letter SAI-SWT-0051 of 05/09/03. Sainco sent rev 1 by email of 6/26/03 and letter SAI-SWT-0087 on 06/26/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. Sainco sent rev 2 by letter SAI-SWT-0158 on of 9/15/03. Telvent sent rev 3 by letter SAI-SWT-0249 of 3/12/04. | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing - Sample Conditioning Rack of Condenser Sampling System Unit 2 | 04360.MS039. 5-22303 | 0 | PN | 2004-11-30 | Telvent | [7 empty] | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Sample Conditioning Rack of Condenser Sampling System Unit 1 | 04360.MS039. 5-12304 | 2 | CC |  |  | 2 | 23/04/04 | 10/08/03 02/10/04 04/27/04 | SWT-SAI-0122 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/01/03 and letter SAI-SWT-0129 of 07/31/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0194 of 11/28/03. Telvent sent rev 2 by letter SAI-SWT-0251 of 3/17/04. | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Sample Conditioning Rack of Condenser Sampling System Unit 2 | 04360.MS039. 5-22304 | 0 | PN | Final panel | Telvent | [7 empty] | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing – Analyzer Panel of Condenser Sampling System Unit 1 | 04360.MS039. 5-12310 | 2 | CC |  |  | 2 | 23/04/04 | 10/28/03 02/10/04 04/27/04 | SWT-SAI-0129 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/01/03 and letter SAI-SWT-0132 of 08/01/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0189 of 11/21/03. Telvent sent rev 2 by letter SAI-SWT-0242 of 02/25/04.
|  | #REF! |  | Dimensioned Outline Drawing – Analyzer Panel of Condenser Sampling System Unit 2 | 04360.MS039. 5-22310 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04.
|  | #REF! |  | Equipment Layout Drawing – Analyzer Panel of Condenser Sampling System Unit 1 | 04360.MS039. 5-12311 | 3 | CC |  |  | 2 | 23/04/04 | 10/28/03 02/10/04 04/27/04 | SWT-SAI-0129 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/01/03 and letter SAI-SWT-0132 of 08/01/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0194 of 11/28/03. Sainco sent rev 2 by letter SAI-SWT-0247 of 3/23/04. Telvent sent rev 3 by letter SAI-SWT-0310 of 10/10/04.
|  | #REF! |  | Equipment Layout Drawing – Analyzer Panel of Condenser Sampling System Unit 2 | 04360.MS039. 5-22311 | 0 | CC | [8 empty] | Telvent sent rev 0 letter SAI-SWT-0327 of 11/23/04.
|  | #REF! |  | Cross Sectional Drawing - Primary Sampling Cooling Panels of Condenser System Unit 1 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Cross Sectional Drawing - Primary Sampling Cooling Panels of Condenser System Unit 2 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing - Sampling Panel with Secundary Sampling Cooling of Condenser System Unit 1 | 04360.MS039. 5-12305 |  | OR | [8 empty] | Sampling will be included in the same Panel | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing - Sampling Panel with Secundary Sampling Cooling of Condenser System Unit 2 | 04360.MS039. 5-22305 |  | OR | [8 empty] | Sampling will be included in the same Panel | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Sampling Panel with Secundary Sampling Cooling of Condenser System Unit 1 | 04360.MS039. 5-12306 |  | OR | [8 empty] | Sampling will be included in the same Panel | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Sampling Panel with Secundary Sampling Cooling of Condenser System Unit 2 | 04360.MS039. 5-22306 |  | OR | [8 empty] | Sampling will be included in the same Panel | JBG/JCL
|  | #REF! |  | Cross Sectional Drawing - Sampling Panel with Secundary Sampling Cooling of Condenser System Unit 1 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Cross Sectional Drawing - Sampling Panel with Secundary Sampling Cooling of Condenser System Unit 2 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing - Control & Recorder Panel of Condenser Sampling System Unit 1 | 04360.MS039. 5-12307 | 3 | CC |  |  | 3 | 23/04/04 | 05/21/03 10/28/03 02/10/04 04/27/04 | SWT-SAI-0054 SWT-SAI-0129 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 4/3/03 and letter SAI-SWT-0033 of 04/10/03. Sainco sent rev 1 by email of 08/01/03 and letter SAI-SWT-0132 of 08/01/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 2 by letter SAI-SWT-0189 of 11/21/03. Telvent sent rev 3 by letter SAI-SWT-0242 of 02/25/04. | JBG/JCL
|  | #REF! |  | Dimensioned Outline Drawing - Control & Recorder Panel of Condenser Sampling System Unit 2 | 04360.MS039. 5-22307 | 0 | PN | 2004-11-08 | Telvent | [7 empty] | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Control & Recorder Panel of Condenser Sampling System Unit 1 | 04360.MS039. 5-12308 | 2 | CC |  |  | 2 | 23/04/04 | 10/28/03 02/10/04 04/27/04 | SWT-SAI-0129 SWT-SAI-0157 SWT-SAI-0207 |  |  | Sainco sent rev 0 by email of 08/01/03 and letter SAI-SWT-0132 of 08/01/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 1 by letter SAI-SWT-0190 of 11/24/03. Telvent sent rev 2 by letter SAI-SWT-0240 of 2/23/04. | JBG/JCL
|  | #REF! |  | Equipment Layout Drawing - Control & Recorder Panel of Condenser Sampling System Unit 2 | 04360.MS039. 5-22308 | 0 | PN | final panel | Telvent | [7 empty] | JBG/JCL
|  | #REF! |  | Cross Sectional Drawing - Control & Recorder Panel of Condenser System Unit 1 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Cross Sectional Drawing - Control & Recorder Panel of Condenser System Unit 2 |  |  | OR | [8 empty] | Included in the Dimensional Drawings and Equipment Layout Drawings | JBG/JCL
|  | #REF! |  | Panels Grounding Details Unit 1 | 04360.MS039. 5-12401 | 3 | CC |  |  | 1 | 2004-07-01 | 05/18/04 08/16/04 10/05/04 11/10/04 | SWT-SAI-0211 SWT-SAI-0227 SWT-SAI-0236 email JW S&W |  |  | Telvent sent rev 0 by letter SAI-SWT-0264 of 4/5/04. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0295 of 09/01/04. Telvent sent rev 3 by letter SAI-SWT-0323 of 11/05/04 and letter SAI-SWT-0323-R1 of 11/11/04
|  | #REF! |  | Panels Grounding Details Unit 2 | 04360.MS039. 5-22401 | 0 | OR | [8 empty] | The document for Unit 1 is applicable also to the Unit 2
|  | #REF! |  | Foundation loads requirements | 04360.MS039. 6-01001 | 0 | OR | [8 empty] | To be included in specific documents for each panel | JBG/JCL
|  | #REF! |  | Equipment load requirements |  |  | OR | [8 empty] | To be included in the Seismic Calculations | JBG/JCL
|  | #REF! |  | Certified bolt location drawings | 04360.MS039. 5-01001 | 2 | CC |  |  |  |  | 1/30/03 4/08/03 10/05/04 | SWT-SAI-0026 SWT-SAI-0042 SWT-SAI-0236 |  |  | Sainco sent rev 0 by email of 01/09/03 and letter SAI-SWT-0012 of 01/15/03. Sainco sent rev 1 by email of 03/05/03 and letter SAI-SWT-0026 of 03/13/03. Sainco will issue final revision when all mechanical drawings are approved. Telvent sent rev 2 by letter SAI-SWT-0293 of 07/29/04 | JBG/JCL
|  | #REF! | [14 empty] | JBG/JCL
|  | #REF! |  | Seismic Calculations | 04360.MS039. 6-02001 | 0 | OR | [8 empty] | To be included in specific documents for each panel | JBG/JCL
|  | #REF! |  | Stress design load calculation | 04360.MS039. 6-02002 | 0 | OR | [8 empty] | To be included in specific documents for each panel | JBG/JCL
|  | #REF! | [14 empty] | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Remote Sampling Cooling Panel of Turbine Sampling System. | 04360.MS039 6-02001 | 2 | CC |  | Telvent Unit 2 |  |  | 03/11/03 06/30/03 09/29/03 | SWT-SAI-0033 SWT-SAI-0078 SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 2/19/03 and letter SAI-SWT-0020 on 02/24/03. Sainco sent rev 1 by email of 5/13/03 and letter SAI-SWT-0052 on 05/12/03. Sainco sent rev 2 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Sample Conditioning Rack of Turbine Sampling System. | 04360.MS039 6-02002 | 2 | CC |  | Telvent Unit 2 |  |  | 03/21/03 06/30/03 09/29/03 | SWT-SAI-0037 SWT-SAI-0079 SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 3/6/03 and letter SAI-SWT-0022 of 03/6/03. Sainco sent rev 1 by email of 5/28/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent rev 2 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Control and Recorder Panel of Turbine Sampling System. | 04360.MS039 6-02003 | 2 | CC |  | Telvent Unit 2 |  |  | 03/21/03 06/30/03 09/29/03 | SWT-SAI-0038 SWT-SAI-0079 SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 3/7/03 and letter SAI-SWT-0025 of 03/10/03. Sainco sent rev 1 by email of 5/28/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent rev 2 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Chiller Equipment Panel of Turbine Sampling System | 04360.MS039 6-02004 | 0 | CC |  | Telvent Unit 2 |  |  | 09/29/03 | SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Analyzer Panel of Turbine Sampling System | 04360.MS039 6-02005 | 0 | CC |  | Telvent Unit 2 |  |  | 09/29/03 | SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Sample Conditioning Rack of Condensate Polishing Sampling System. | 04360.MS039 6-02101 | 1 | CC |  | Telvent Unit 2 |  |  | 04/08/03 09/29/03 | SWT-SAI-0042 SWT-SAI-0101 |  |  | Sainco sent rev 0 by letter SAI-SWT-0026 of 03/13/03. Sainco sent rev 1 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Control and Recorder Panel of Condensate Polishing Sampling System. | 04360.MS039 6-02102 | 2 | CC |  | Telvent Unit 2 |  |  | 04/07/03 06/30/03 09/29/03 | SWT-SAI-0041 SWT-SAI-0079 SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 20/3/03 and letter SAI-SWT-0028 of 19/3/03. Sainco sent rev 1 by email of 5/28/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent rev 2 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Chiller Equipment Panel of Condensate Polishing Sampling System. | 04360.MS039 6-02103 | 0 | CC |  | Telvent Unit 2 |  |  | 09/29/03 | SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Analyzer Panel of Condensate Polishing Sampling System. | 04360.MS039 6-02104 | 0 | CC |  | Telvent Unit 2 |  |  | 09/29/03 | SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Sample Conditioning Rack of Auxiliary Boiler Sampling System. | 04360.MS039 6-02201 | 0 | CC |  | Telvent Unit 2 |  |  | 04/07/03 08/25/03 10/24/03 | SWT-SAI-0041 SWT-SAI-0092 SWT-SAI-0128 |  |  | Sainco sent rev 0 by email of 20/3/03 and letter SAI-SWT-0028 of 19/3/03. Sainco sent rev 1 by email of 06/03/03 and letter SAI-SWT-0072 of 6/4/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Sainco sent rev 2 by email of 09/04/03 and letter SAI-SWT-0149 of 9/3/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Control and Recorder Panel of Auxiliary Boiler Sampling Panel. | 04360.MS039 6-02202 | 2 | CC |  | Telvent Unit 2 |  |  | 04/07/03 06/30/03 09/29/03 | SWT-SAI-0041 SWT-SAI-0079 SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 20/3/03 and letter SAI-SWT-0028 of 19/3/03. Sainco sent rev 1 by email of 5/28/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent rev 2 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03.Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Analyzer Panel of Auxiliary Boiler Sampling Panel. | 04360.MS039 6-02203 | 0 | CC |  | Telvent Unit 2 |  |  | 09/29/03 10/01/03 | SWT-SAI-0101 SWT-SAI-0120 |  |  | Sainco sent rev 0 by email of 08/05/03 and letter SAI-SWT-0135 on 08/05/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Sample Conditioning Rack of Condenser Sampling System. | 04360.MS039 6-02301 | 2 | CC |  | Telvent Unit 2 |  |  | 04/07/03 06/30/03 09/29/03 | SWT-SAI-0041 SWT-SAI-0079 SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 20/3/03 and letter SAI-SWT-0028 of 19/3/03. Sainco sent rev 1 by email of 5/28/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent rev 2 by email of 08/05/03 and letter SAI-SWT-0125-R1 on 08/05/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Control and Recorder Panel of Condenser Sampling System. | 04360.MS039 6-02302 | 2 | CC |  | Telvent Unit 2 |  |  | 05/19/03 06/06/03 09/29/03 | SWT-SAI-0053 SWT-SAI-0066 SWT-SAI-0101 |  |  | Sainco sent rev 0 by letter SAI-SWT-0037 of 4/23/03. Sainco sent rev 1 by letter SAI-SWT-0062 of 5/22/03. Sainco sent rev 2 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Calculations for Seismic Requirements, Stress Design Loads, Foundation Loads and Bolts – Analyzer Panel of Condenser Sampling System. | 04360.MS039 6-02303 | 0 | CC |  | Telvent Unit 2 |  |  | 09/29/03 | SWT-SAI-0101 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG/JCL
|  | #REF! |  | Remote and Primary Sample Coolers Design Report | 04360.MS039 6-08001 | 3 | CC |  | Telvent Unit 2 |  |  | 07/03/03 02/02/04 03/12/04 06/11/04 | SWT-SAI-0084 SWT-SAI-0155 SWT-SAI-0179 SWT-SAI-0215 |  |  | Sainco sent rev 0 by letter SAI-SWT-0074 of 6/6/03 and email of 6/6/03. Sainco sent rev 1 by letter SAI-SWT-0138 of 8/6/03 and email of 8/6/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 2 by letter SAI-SWT-0233 of 2/12/04. Telvent sent rev 3 by letter SAI-SWT-0262 of 03/30/04. | JGG
|  | #REF! |  | Secondary Sample Cooling Design Report | 04360.MS039 6-08002 | 0 | CC |  | Telvent Unit 2 |  |  | 08/21/03 | SWT-SAI-0091 |  |  | Sainco sent rev 0 by letter SAI-SWT-0092 of 7/2/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. | JGG
|  | #REF! |  | Report of Heat Transfer from Turbine Sampling System and Condensate Polishing Sampling System Equipment | 04360.MS039 6-08003 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0325 of 11/12/04
#REF!
|  | #REF! |  | Hydraulic Performance calculations | 04360.MS039. 6-02402 |  | OR | [8 empty] | This document is not applicable for this supply, because there are not big pipes nor pumps.
|  | #REF! |  | Pump Data Sheets (Certified) | 04360.MS039. 6-02004 |  | OR | [8 empty] | This information be included in the "Equipment and Instruments Data Sheets"
|  | #REF! |  | Induction Motor Data Sheets (Certified) | 04360.MS039. 6-03001 |  | OR | [8 empty] | This information will be included in the "Equipment and Instruments Data Sheets"
|  | #REF! |  | Certificates of instruments | 04360.MS039. 6-04001 |  | OR | [8 empty] | This information will be included in the "Mill test certificates"
|  | #REF! |  | Painting Procedures | 04360.MS039. 7-00010 |  | OR | [8 empty] | Replaced by document Surface Treatment, Priming and Painting ref. 04360.MS039. 4-00005
|  | #REF! |  | Sampling Lines Design Report | 04360.MS039. 6-02500 | 3 | CC |  |  |  |  | 05/30/03 06/30/03 12/01/03 03/15/04 06/11/04 | SWT-SAI-0060 SWT-SAI-0078 SWT-SAI-0139 SWT-SAI-0180 SWT-SAI-0215 |  |  | Sainco sent rev 0 by email of 5/13/03 and letter SAI-SWT-0052 on 05/12/03. Sainco sent rev 1 by email of 08/08/03 and letter SAI-SWT-0141 of 08/08/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 2 by letter SAI-SWT-0208 of 1/14/04. Telvent sent rev 3 by letter SAI-SWT-0262 of 03/30/04 | JGG
|  | #REF! |  | Specification of Piping and Tubing within the Sampling Panels | 04360.MS039. 6-02510 | 1 | CC |  | Telvent Unit 2 | 1 | 23/04/04 | 12/12/03 12/31/03 | SWT-SAI-0142 SWT-SAI-0147 |  |  | Sainco sent rev 0 by letter SAI-SWT-0141 of 08/08/03 (Attachment 3 of document Sampling Lines Design Report ref 04360.MS039. 6-02500 rev 1) . Sainco sent rev 1 by letter SAI-SWT-0200 of 12/15/03 | JGG
#REF!
|  | #REF! |  | 4. Detail Design - Electrical, Instrumentation and Control
|  | #REF! |  | PLC/MMI Hardware Architecture Drawing Unit 1 | 04360.MS039. 5-14001 | 5 | RE | 2004-03-01 | Telvent |  |  | 11/15/02 12/17/02 4/25/03 5/26/03 6/5/03 2/16/04 | SWT-SAI-0017 SWT-SAI-0022 SWT-SAI-0048 SWT-SAI-0056 SWT-SAI-0063 SWT-SAI-0159 |  |  | Sainco sent rev 0 by email of 10/29/02 and letters SAI-TPC-0016 / SAI-SWT-0005 of 11/4/02. Sainco sent rev 1 and related Catalog Information by email of 11/20/02 and by letter SAI-SWT-0010 of 11/28/02. Sainco sent rev 2 by email and letter SAI-SWT-0029 of 3/21/03. Sainco sent rev 3 by letter SAI-SWT-0041 of 5/14/03 (Not required response) . Sainco sent rev 4 by letter SAI-SWT-0041 of 4/29/03 and email of 4/30/03. Sainco sent fax SAI-SWT-0068 of 5/28/03. Telvent sent rev 5 by letter SAI-SWT-0191 of 11/26/03. | JBG
|  | #REF! |  | PLC/MMI Hardware Architecture Drawing Unit 2 | 04360.MS039. 5-24001 | 0 | PN | 2004-06-01 | Telvent
|  | #REF! |  | PLC/MMI Iist of material | 04360.MS039. 5-04002 |  | OR | [8 empty] | Replaced by document "Equipment and Instrument Lists Unit 1 and Unit 2"
|  | #REF! |  | PLC Module switch / jumpers arrangement drawing |  |  | OR | [8 empty] | There are no switches in the PLC
|  | #REF! |  | Internal and External wiring - Turbine Sampling System Panels Unit 1 | 04360.MS039. 5-13001 | 2 | RE | 2004-12-02 | Telvent | 2 |  | 11/25/03 08/16/04 11/18/04 | SWT-SAI-0134 SWT-SAI-0227 SWT-SAI-0242 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0311 of 10/11/04. | GGT
|  | #REF! |  | Internal and External wiring - Turbine Sampling System Panels Unit 2 | 04360.MS039. 5-23001 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Internal and External Wiring - Chiller Equipment of Turbine Sampling System Unit 1 | 04360.MS039. 5-13002 | 2 | RE | 2004-12-02 | Telvent | 2 |  | 11/25/03 08/16/04 11/18/04 | SWT-SAI-0134 SWT-SAI-0227 SWT-SAI-0242 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0311 of 10/11/04. | GGT
|  | #REF! |  | Internal and External Wiring - Chiller Equipment of Turbine Sampling System Unit 2 | 04360.MS039. 5-23002 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Internal and External wiring - Condensate Polishing Sampling System Panels Unit 1 | 04360.MS039. 5-13100 | 2 | RE | 2004-12-02 | Telvent | 2 |  | 11/25/03 08/16/04 11/18/04 | SWT-SAI-0134 SWT-SAI-0227 SWT-SAI-0242 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0311 of 10/11/04. | GGT
|  | #REF! |  | Internal and External wiring - Condensate Polishing Sampling System Panels Unit 2 | 04360.MS039. 5-23100 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Internal and External Wiring - Chiller Equipment of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-13101 | 2 | RE | 2004-12-02 | Telvent | 2 |  | 11/25/03 08/16/04 11/18/04 | SWT-SAI-0134 SWT-SAI-0227 SWT-SAI-0242 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0311 of 10/11/04. | GGT
|  | #REF! |  | Internal and External Wiring - Chiller Equipment of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-23101 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Internal and External wiring - Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-13200 | 2 | RE | 2004-12-02 | Telvent | 2 |  | 11/25/03 08/16/04 11/18/04 | SWT-SAI-0134 SWT-SAI-0227 SWT-SAI-0242 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0311 of 10/11/04. | GGT
|  | #REF! |  | Internal and External wiring - Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-23200 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Internal and External wiring - Condenser Sampling System Unit 1 | 04360.MS039. 5-13300 | 2 | RE | 2004-12-02 | Telvent | 2 |  | 11/25/03 08/16/04 11/18/04 | SWT-SAI-0134 SWT-SAI-0227 SWT-SAI-0242 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03. Telvent sent rev 1 by letter SAI-SWT-0286 of 07/08/04. Telvent sent rev 2 by letter SAI-SWT-0311 of 10/11/04. | GGT
|  | #REF! |  | Internal and External wiring - Condenser Sampling System Unit 2 | 04360.MS039. 5-23300 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Wiring - Conduits Lists Turbine Sampling System Panels Unit 1 | 04360.MS039. 6-13500 | 0 | RE | 2004-11-09 | Telvent | 0 | 2004-01-07 | 2004-08-16 | SWT-SAI-0227 |  |  | Telvent sent rev 0 by letter SAI-SWT-0286 of 07/08/04. | GGT
|  | #REF! |  | Wiring - Conduits Lists Turbine Sampling System Panels Unit 2 | 04360.MS039. 6-23500 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Wiring - Conduits Lists Condensate Polishing Sampling System Unit 1 | 04360.MS039. 6-13510 | 0 | RE | 2004-11-09 | Telvent | 0 | 2004-01-07 | 2004-08-16 | SWT-SAI-0227 |  |  | Telvent sent rev 0 by letter SAI-SWT-0286 of 07/08/04. | GGT
|  | #REF! |  | Wiring - Conduits Lists Condensate Polishing Sampling System Unit 2 | 04360.MS039. 6-23510 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Wiring - Conduits Lists Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 6-13520 | 0 | RE | 2004-11-09 | Telvent | 0 | 2004-01-07 | 2004-08-16 | SWT-SAI-0227 |  |  | Telvent sent rev 0 by letter SAI-SWT-0286 of 07/08/04. | GGT
|  | #REF! |  | Wiring - Conduits Lists Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 6-23520 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | Wiring - Conduits Lists Condenser Sampling System Unit 1 | 04360.MS039. 6-13530 | 0 | RE | 2004-11-09 | Telvent | 0 | 2004-01-07 | 2004-08-16 | SWT-SAI-0227 |  |  | Telvent sent rev 0 by letter SAI-SWT-0286 of 07/08/04. | GGT
|  | #REF! |  | Wiring - Conduits Lists Condenser Sampling System Unit 2 | 04360.MS039. 6-23530 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Internal Wiring - Turbine Sampling System Unit 1 | 04360.MS039. 5-13010 | 0 | RE | 12/09/03 | Telvent | 0 | 23/04/04 | 11/25/03 | SWT-SAI-0134 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03 | GGT
|  | #REF! |  | PLC Internal Wiring - Turbine Sampling System Unit 2 | 04360.MS039. 5-23010 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Internal Wiring - Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-13110 | 0 | RE | 12/09/03 | Telvent | 0 | 23/04/04 | 11/25/03 | SWT-SAI-0134 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03 | GGT
|  | #REF! |  | PLC Internal Wiring - Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-23110 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Internal Wiring - Auxiliary Boiler Sampling System Unit 1 | 04360.MS039. 5-13210 | 0 | RE | 12/09/03 | Telvent | 0 | 23/04/04 | 11/25/03 | SWT-SAI-0134 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03 | GGT
|  | #REF! |  | PLC Internal Wiring - Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-23210 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Internal Wiring - Condenser Sampling System Unit 1 | 04360.MS039. 5-13310 | 0 | RE | 12/09/03 | Telvent | 0 | 23/04/04 | 11/25/03 | SWT-SAI-0134 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03 | GGT
|  | #REF! |  | PLC Internal Wiring - Condenser Sampling System Unit 2 | 04360.MS039. 5-23310 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC / PC / LAN Wiring Unit 1 | 04360.MS039. 5-13400 | 0 | RE | 12/09/03 | Telvent | 0 | 23/04/04 | 11/25/03 | SWT-SAI-0134 |  |  | Sainco sent rev 0 by letter SAI-SWT-0175 of 10/20/03 | JBG
|  | #REF! |  | PLC / PC / LAN Wiring Unit 2 | 04360.MS039. 5-23400 | 0 | PN | Approval Unit 1 | Telvent
#REF!
|  | #REF! |  | Plan View and Conduit Plan panels of Turbine Sampling System Unit 1 and Unit 2 | 04360.MS039. 5-01010 | 0 | PN | 2004-11-05 | Telvent | [7 empty] | JGG
|  | #REF! |  | Plan View and Conduit Plan panels of Condensate Polishing Sampling System Unit 1 and Unit 2 | 04360.MS039. 5-01020 | 0 | PN | 2004-11-12 | Telvent | [7 empty] | JGG
|  | #REF! |  | Plan View and Conduit Plan panels of Auxiliary Boiler Sampling System Unit 1 and Unit 2 | 04360.MS039. 5-01030 | 0 | PN | 2004-11-12 | Telvent | [7 empty] | JGG
|  | #REF! |  | Plan View and Conduit Plan panels of Condenser Sampling System Unit 1 and Unit 2 | 04360.MS039. 5-01040 | 0 | PN | 2004-11-12 | Telvent | [7 empty] | JGG
|  | #REF! |  | Conduit Plan for installation of FO LAN Unit 1 and Unit 2 | 04360.MS039. 5-01050 | 0 | PN | 2004-11-30 | Telvent | [7 empty] | JGG
#REF!
#REF!
|  | #REF! |  | P & ID - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360.MS039. 5-14001 | 0 | OR |  |  |  |  | 11/12/02 01/28/03 03/20/03 | SWT-SAI-0021 e-mail SWT-SAI-0036 |  |  | Sainco sent rev 0 by email of 10/30/02 and letters SAI-TPC-0017 / SAI-SWT-0006 of 11/4/02. Sainco sent email of 12/13/02. Drawing 04360.MS039. 5-14001 has been replaced by drawings 04360-1G62-M2116 and 04360-1G62-M2117 | JBG/JCL
|  | #REF! |  | P & ID - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360-1G62-M2116 | 5 | CC |  |  | 5 | 23/04/04 | 11/12/02 01/28/03 03/20/03 05/21/03 08/25/03 02/02/04 06/25/04 | SWT-SAI-0021 e-mail SWT-SAI-0036 SWT-SAI-0054 SWT-SAI-0092 SWT-SAI-0154 SWT-SAI-0217 |  |  | Sainco sent rev 1 by email of 1/15/03 and letter SAI-SWT-0014 of 1/27/03. Sainco sent rev 2 by email of 4/2/03 and letter SAI-SWT-0033 of 04/10/03. Sainco sent rev 3 by letter SAI-SWT-0051 of 05/09/03 (not valid, witdrawn by by letter SAI-SWT-0060 of 5/16/03). Sainco sent rev 3 by email of 05/23/03 and letter SAI-SWT-0072 of 6/4/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Sainco sent rev 4 by email of 08/13/03 and letter SAI-SWT-0145 of 8/12/03. Sainco sent fax SAI-SWT-0151 of 9/8/03 and SAI-SWT-0152 of 9/9/03. Telvent sent rev 5 letter SAI-SWT-0231 of 02/09/04. | JBG/JCL
|  | #REF! |  | P & ID - Remote Sampling Cooling Panels of Turbine Sampling System Unit 1 | 04360-1G62-M2117 | 5 | CC |  |  | 5 | 23/04/04 | 11/12/02 01/28/03 03/20/03 05/21/03 08/25/03 02/02/04 06/25/04 | SWT-SAI-0021 e-mail SWT-SAI-0036 SWT-SAI-0054 SWT-SAI-0092 SWT-SAI-0154 SWT-SAI-0217 |  |  | Sainco sent rev 1 by email of 1/15/03 and letter SAI-SWT-0014 of 1/27/03. Sainco sent rev 2 by email of 4/2/03 and letter SAI-SWT-0033 of 04/10/03. Sainco sent rev 3 by letter SAI-SWT-0051 of 05/09/03 (not valid, witdrawn by by letter SAI-SWT-0060 of 5/16/03). Sainco sent rev 3 by email of 05/23/03 and letter SAI-SWT-0072 of 6/4/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Sainco sent rev 4 by email of 08/13/03 and letter SAI-SWT-0145 of 8/12/03. Sainco sent fax SAI-SWT-0151 of 9/8/03 and SAI-SWT-0152 of 9/9/03. Telvent sent rev 5 letter SAI-SWT-0231 of 02/09/04. | JBG/JCL
|  | #REF! |  | P & ID - Remote Sampling Cooling Panels of Turbine Sampling System Unit 2 | 04360.MS039. 5-24001 | 0 | OR | [8 empty] | The P&IDs Unit 1 are applicable to both the Unit 1 and the Unit 2 | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Turbine Sampling System Unit 1 | 04360.MS039. 5-14002 | 0 | OR |  |  |  |  | 2002-12-11 | SWT-SAI-0021 |  |  | Sainco sent rev 0 by email of 10/30/02 and letters SAI-TPC-0017 / SAI-SWT-0006 of 11/4/02. Drawing 04360.MS039. 5-14002 has been replaced by drawings 04360-1G62-M2118 and 04360-1G62-M2119 | JBG/JCL
|  | #REF! |  | P & ID - Sample Conditioning Rack of Turbine Sampling System Unit 1 | 04360-1G62-M2118 | 3 | RE | 2004-02-27 | TPC | 3 | 23/04/04 | 12/11/02 09/18/03 09/22/03 02/05/04 | SWT-SAI-0021 SWT-SAI-0096 SWT-SAI-0097 SWT-SAI-0156 |  |  | Sainco sent rev 1 by email of 4/3/03 (not valid due to error detected in symbol). Sainco sent rev 1 by email of 05/20/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Sainco sent rev 2 by email and letter SAI-SWT-0158 on of 9/15/03. Telvent sent rev 3 by letter SAI-SWT-0234 on of 2/13/04. | JBG/JCL
|  | #REF! |  | P & ID - Sample Conditioning Rack of Turbine Sampling System Unit 1 | 04360-1G62-M2119 | 3 | RE | 2004-02-27 | TPC | 3 | 23/04/04 | 12/11/02 09/18/03 09/22/03 02/05/04 | SWT-SAI-0021 SWT-SAI-0096 SWT-SAI-0097 SWT-SAI-0156 |  |  | Sainco sent rev 1 by email of 05/20/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Sainco sent rev 2 by email and letter SAI-SWT-0158 on of 9/15/03. Telvent sent rev 3 by letter SAI-SWT-0234 on of 2/13/04. | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Turbine Sampling System Unit 2 | 04360.MS039. 5-24002 | 0 | OR | [8 empty] | The P&IDs Unit 1 are applicable to both the Unit 1 and the Unit 2 | JBG/JCL
|  | #REF! |  | P&ID - Chiller Equipment of Turbine Sampling System Unit 1 | 04360.MS039. 5-14003 | 0 | OR | [8 empty] | Chiller Equipment will be included in P & ID - Sampling Cooling and Analysis Panel of Turbine Sampling System Unit 1 | JBG/JCL
|  | #REF! |  | P&ID - Chiller Equipment of Turbine Sampling System Unit 2 | 04360.MS039. 5-24003 | 0 | OR | [8 empty] | Chiller Equipment will be included in P & ID - Sampling Cooling and Analysis Panel of Turbine Sampling System Unit 2 | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-14102 | 0 | OR |  |  |  |  | 12/11/02 03/14/03 | SWT-SAI-0021 SWT-SAI-0034 |  |  | , | JBG/JCL
|  | #REF! |  | P & ID - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 1 | 04360-1G62-M2120 | 5 | RE | 2004-02-27 | TPC | 5 | 23/04/04 | 12/11/02 03/14/03 09/22/03 02/05/04 | SWT-SAI-0021 SWT-SAI-0034 SWT-SAI-0097 SWT-SAI-0156 |  |  | Sainco sent rev 1 by email of 1/27/03 and letter SAI-SWT-0019 of 2/17/03. Sainco sent rev 2 (Not required response) by email of 04/11/03 and letter SAI-SWT-0057 of 5/15/03. Sainco sent rev 3 by email of 5/26/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Rev 4 is delayed until receiving comments from TPC to 04360-1G62-M2121 rev 3. Sainco sent rev 4 by SAI-SWT-0196 of 12/03/03. Telvent sent rev 5 by letter SAI-SWT-0234 on of 2/13/04. | JBG/JCL
|  | #REF! |  | P & ID - Sample Conditioning Rack of Condensate Polishing Sampling System Unit 1 | 04360-1G62-M2121 | 5 | RE | 2004-02-27 | TPC | 5 | 23/04/04 | 12/11/02 03/14/03 06/19/03 09/18/03 10/29/03 02/05/04 | SWT-SAI-0021 SWT-SAI-0034 SWT-SAI-0072 SWT-SAI-0096 SWT-SAI-0130 SWT-SAI-0156 |  |  | Sainco sent rev 1 by email of 1/27/03 and letter SAI-SWT-0019 of 2/17/03. Sainco sent rev 2 by letter SAI-SWT-0058 of 5/15/03 and email of 05/20/03. Sainco sent rev 3 by email of 08/08/03 and letter SAI-SWT-0141 of 08/08/03.Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 4 by SAI-SWT-0196 of 12/03/03. Telvent sent rev 5 by letter SAI-SWT-0234 on of 2/13/04. | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-24102 | 0 | OR | [8 empty] | The P&IDs Unit 1 are applicable to both the Unit 1 and the Unit 2 | JBG/JCL
|  | #REF! |  | P&ID - Chiller Equipment of Condensate Polishing Sampling System Unit 1 | 04360.MS039. 5-14103 | 0 | OR | [8 empty] | Chiller Equipment will be included in P & ID - Sampling Cooling and Analysis Panel of Condensate Polishing Sampling System Unit 1 | JBG/JCL
|  | #REF! |  | P&ID - Chiller Equipment of Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-24103 | 0 | OR | [8 empty] | Chiller Equipment will be included in P & ID - Sampling Cooling and Analysis Panel of Condensate Polishing Sampling System Unit 2 | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Auxiliary Boiler Sampling Unit 1 | 04360.MS039. 5-14202 | 0 | OR |  |  |  |  | 11/19/02 12/11/02 02/27/03 | e-mail SWT-SAI-0021 SWT-SAI-0030 |  |  | Sainco sent rev 0 by email of 10/30/02 and letters SAI-TPC-0017 / SAI-SWT-0006 of 11/4/02. Drawing 04360.MS039. 5-14202 has been replaced by drawing 04360-1G62-M2122 | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Auxiliary Boiler Sampling Unit 1 | 04360-1G62-M2122 | 4 | RE | 2004-03-03 | TPC | 4 | 23/04/04 | 11/19/02 12/11/02 02/27/03 09/22/03 02/05/04 | e-mail SWT-SAI-0021 SWT-SAI-0030 SWT-SAI-0097 SWT-SAI-0156 |  |  | Sainco sent rev 1 by email of 12/10/02 (not valid). Sainco sent rev 1 by email of 2/5/03 and by letter SAI-SWT-0017 on 02/07/03. Sainco sent rev 2 by email of 05/20/03 and letter SAI-SWT-0067 of 05/26/03. Sainco sent letter SAI-SWT-0124 of 7/24/03. Sainco sent rev 3 by letter SAI-SWT-0177 of 11/3/03. Telvent sent rev 4 by letter SAI-SWT-0237 of 02/17/04 | JBG/JCL
|  | #REF! |  | P & ID - Sampling Cooling and Analysis Panel of Auxiliary Boiler Sampling Unit 2 | 04360.MS039. 5-24202 | 0 | OR | [8 empty] | The P&IDs Unit 1 are applicable to both the Unit 1 and the Unit 2 | JBG/JCL
|  | #REF! |  | P & ID - Sampling and Analysis Panel of Condenser Sampling System Unit 1 | 04360.MS039. 5-14302 | 0 | OR |  |  |  |  | 12/11/02 03/11/03 | SWT-SAI-0021 SWT-SAI-0033 |  |  | Sainco sent rev 0 by email of 10/30/02 and letters SAI-TPC-0017 / SAI-SWT-0006 of 11/4/02. Drawing 04360.MS039. 5-14302 has been replaced by drawing 04360-1G62-M2123 | JBG/JCL
|  | #REF! |  | P & ID - Sample Conditioning Rack of Condenser Sampling System Unit 1 | 04360-1G62-M2123 | 4 | RE | 2004-03-03 | TPC | 4 | 23/04/04 | 12/11/02 03/11/03 08/21/03 02/05/04 | SWT-SAI-0021 SWT-SAI-0033 SWT-SAI-0091 SWT-SAI-0156 |  |  | Sainco sent rev 1 by email of 2/18/03 and letter SAI-SWT-0020 on 02/24/03. Sainco sent rev 2 by email of 6/18/03 and letter SAI-SWT-0087 on 06/26/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. Sainco sent rev 3 by email and letter SAI-SWT-0158 on of 9/15/03. Telvent sent rev 4 by letter SAI-SWT-0237 of 02/17/04 | JBG/JCL
|  | #REF! |  | P & ID - Sample Conditioning Rack of Condenser Sampling System Unit 2 | 04360.MS039. 5-24302 | 0 | OR | [8 empty] | The P&IDs Unit 1 are applicable to both the Unit 1 and the Unit 2 | JBG/JCL
|  | #REF! |  | P & ID - Fundamental Systems Interconnection Diagram Unit 1 | 04360.MS039. 5-14401 | 0 | OR |  |  |  |  | 03/20/03 | SWT-SAI-0036 |  |  | Sainco sent rev 0 by email of 1/16/03 and letter SAI-SWT-0014 of 1/27/03. Drawing 04360.MS039. 5-14401 has been replaced by drawings 04360-1G62-M2124 and 04360-1G62-M2125 | JBG/JCL
|  | #REF! |  | P & ID - Fundamental Systems Interconnection Diagram Unit 1 | 04360-1G62-M2124 | 1 | CC | 2004-11-08 | Telvent | 1 | 23/04/04 | 03/20/03 05/21/03 | SWT-SAI-0036 SWT-SAI-0054 |  |  | Sainco sent rev 1 by email of 4/3/03 and letter SAI-SWT-0033 of 04/10/03. Sainco will issue final revision after all PIDs are approved | JBG/JCL
|  | #REF! |  | P & ID - Fundamental Systems Interconnection Diagram Unit 1 | 04360-1G62-M2125 | 1 | CC | 2004-11-08 | Telvent | 1 | 23/04/04 | 03/20/03 05/21/03 | SWT-SAI-0036 SWT-SAI-0054 |  |  | Sainco sent rev 1 by email of 4/3/03 and letter SAI-SWT-0033 of 04/10/03. Sainco will issue final revision after all PIDs are approved | JBG/JCL
|  | #REF! |  | P & ID - Fundamental Systems Interconnection Diagram Unit 2 | 04360.MS039. 5-24401 | 0 | OR | [8 empty] | The P&IDs Unit 1 are applicable to both the Unit 1 and the Unit 2 | JBG/JCL
|  | #REF! |  | Control Logic Diagram - Turbine Sampling System Unit 1 | 04361.MS039. 5-14611 | 1 | RE | 07/29/04 | Telvent |  |  | 04/16/04 15/07/04 | SWT-SAI-0198 SWT-SAI-0218 |  |  | Telvent sent rev 0 by letter SAI-SWT-0250 of 03/15/04. Telvent sent rev 1 by letter SAI-SWT-0282 of 06/04/04. | JBG
|  | #REF! |  | Control Logic Diagram - Turbine Sampling System Unit 2 | 04361.MS039. 5-24611 | 0 | PN | 2003-10-03 | Telvent | [7 empty] | JBG
|  | #REF! |  | Control Logic Diagram - Condensate Polishing Sampling System Unit 1 | 04361.MS039. 5-14612 | 1 | RE | 07/29/04 | Telvent |  |  | 04/16/04 15/07/04 | SWT-SAI-0198 SWT-SAI-0218 |  |  | Telvent sent rev 0 by letter SAI-SWT-0250 of 03/15/04. Telvent sent rev 1 by letter SAI-SWT-0282 of 06/04/04. | JBG
|  | #REF! |  | Control Logic Diagram - Condensate Polishing Sampling System Unit 2 | 04361.MS039. 5-24612 | 0 | PN | 2003-10-03 | Telvent | [7 empty] | JBG
|  | #REF! |  | Control Logic Diagram - Auxiliary Boiler Sampling System Unit 1 | 04361.MS039. 5-14613 | 1 | RE | 07/29/04 | Telvent |  |  | 04/16/04 15/07/04 | SWT-SAI-0198 SWT-SAI-0218 |  |  | Telvent sent rev 0 by letter SAI-SWT-0250 of 03/15/04. Telvent sent rev 1 by letter SAI-SWT-0282 of 06/04/04. | JBG
|  | #REF! |  | Control Logic Diagram - Auxiliary BoilerSampling System Unit 2 | 04361.MS039. 5-24613 | 0 | PN | 2003-10-03 | Telvent | [7 empty] | JBG
|  | #REF! |  | Control Logic Diagram - Condenser Sampling System Unit 1 | 04361.MS039. 5-14614 | 1 | RE | 07/29/04 | Telvent |  |  | 04/16/04 15/07/04 | SWT-SAI-0198 SWT-SAI-0218 |  |  | Telvent sent rev 0 by letter SAI-SWT-0250 of 03/15/04. Telvent sent rev 1 by letter SAI-SWT-0282 of 06/04/04. | JBG
|  | #REF! |  | Control Logic Diagram - Condenser Sampling System Unit 2 | 04361.MS039. 5-24614 | 0 | PN | 2003-10-03 | Telvent | [7 empty] | JBG
|  | #REF! |  | Control Logic Specifications - Turbine Sampling System Unit 1 and Unit 2 | 04360.MS039. 5-14601 | 1 | CC |  | Telvent Unit 2 |  |  | 04/21/03 06/05/03 09/26/03 | SWT-SAI-0044 SWT-SAI-0064 SWT-SAI-0100 |  |  | Sainco sent rev 0 by email of 3/28/03 and letter SAI-SWT-0031 of 3/28/03. Sainco sent fax SAI-SWT-0065 of 5/23/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG
|  | #REF! |  | Control Logic Specifications - Turbine Sampling System Unit 2 | 04360.MS039. 5-24601 | 0 | OR | [8 empty] | The document for Unit 1 is applicable also to the Unit 2 | GGT
|  | #REF! |  | Control Logic Specifications - Condensate Polishing Sampling System Unit 1and Unit 2 | 04360.MS039. 5-14602 | 1 | CC |  | Telvent Unit 2 |  |  | 04/21/03 09/26/03 | SWT-SAI-0044 SWT-SAI-0100 |  |  | Sainco sent rev 0 by email of 3/28/03 and letter SAI-SWT-0031 of 3/28/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG
|  | #REF! |  | Control Logic Specifications - Condensate Polishing Sampling System Unit 2 | 04360.MS039. 5-24602 | 0 | OR | [8 empty] | The document for Unit 1 is applicable also to the Unit 2 | GGT
|  | #REF! |  | Control Logic Specifications - Auxiliary Boiler Sampling System Unit 1and Unit 2 | 04360.MS039. 5-14603 | 1 | CC |  | Telvent Unit 2 |  |  | 04/21/03 09/26/03 | SWT-SAI-0044 SWT-SAI-0100 |  |  | Sainco sent rev 0 by email of 3/28/03 and letter SAI-SWT-0031 of 3/28/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG
|  | #REF! |  | Control Logic Specifications - Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 5-24603 | 0 | OR | [8 empty] | The document for Unit 1 is applicable also to the Unit 2 | GGT
|  | #REF! |  | Control Logic Specifications - Condenser Sampling System Unit 1and Unit 2 | 04360.MS039. 5-14604 | 1 | CC |  | Telvent Unit 2 |  |  | 04/21/03 04/23/03 09/26/03 | SWT-SAI-0044 email SWT-SAI-0100 |  |  | Sainco sent rev 0 by email of 3/28/03 and letter SAI-SWT-0031 of 3/28/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. | JBG
|  | #REF! |  | Control Logic Specifications - Condenser Sampling System Unit 2 | 04360.MS039. 5-24604 | 0 | OR | [8 empty] | The document for Unit 1 is applicable also to the Unit 2 | GGT
|  | #REF! |  | Panels Lists Unit 1 | 04360.MS039. 6-18001 | 1 | CC |  |  | 0 | 23/04/04 | 09/29/03 06/14/04 | SWT-SAI-0101 SWT-SAI-0216 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 1 by letter SAI-SWT-0271 of 5/6/04. | JGG
|  | #REF! |  | Panels Lists Unit 2 | 04360.MS039. 6-28001 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0304 of 10/6/04. | JBG
|  | #REF! |  | Instrumentation Lists Unit 1 | 04360.MS039. 6-18002 | 3 | CC |  |  | 3 | 23/07/04 | 03/28/03 09/26/03 02/10/04 08/10/04 | SWT-SAI-0039 SWT-SAI-0100 SWT-SAI-0157 SWT-SAI-0225 |  |  | Sainco sent rev 0 by email of 3/5/03 and letter SAI-SWT-0023 of 03/6/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 2 by letter SAI-SWT-0190 of 11/24/03. Telvent sent rev 3 by letter SAI-SWT-0288 of 07/19/04. | JGG
|  | #REF! |  | Instrumentation Lists Unit 2 | 04360.MS039. 6-28002 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0304 of 10/6/04. | JBG
|  | #REF! |  | Condenser Sampling Pumps Lists Unit 1 | 04360.MS039. 6-18003 | 2 | CC2 |  |  | 1 | 23/04/04 | 10/01/03 12/22/03 | SWT-SAI-0120 SWT-SAI-0144 |  |  | Sainco sent rev 0 by email of 8/4/03 and letter SAI-SWT-0126 of 07/29/03 (sent again on 8/6/03). Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0173 of 10/17/03 and email of 10/20/03. Telvent sent rev 2 letter SAI-SWT-0276 of 05/19/04. | JGG
|  | #REF! |  | Condenser Sampling Pumps Lists Unit 2 | 04360.MS039. 6-28003 | 0 | OR | [8 empty] | The document for Unit 1 is applicable also to the Unit 2 | JBG
|  | #REF! |  | Secondary Sample Cooling Equipment Lists Unit 1 | 04360.MS039. 6-18004 | 0 | CC |  |  | 0 | 23/04/04 | 08/21/03 | SWT-SAI-0091 |  |  | Sainco sent rev 0 by letter SAI-SWT-0092 of 7/2/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. | JGG
|  | #REF! |  | Secondary Sample Cooling Equipment Lists Unit 2 | 04360.MS039. 6-28004 | 0 | PN |  | Telvent | [6 empty] | The document for Unit 1 is applicable also to the Unit 2 | JBG
|  | #REF! |  | Analyzers / Recorders Lists Unit 1 | 04360.MS039. 6-18005 | 4 | CC |  |  | 3 | 23/04/04 | 08/21/03 10/03/03 12/29/03 03/12/04 06/14/04 | SWT-SAI-0091 SWT-SAI-0121 SWT-SAI-0146 SWT-SAI-0179 SWT-SAI-0216 |  |  | Sainco sent rev 0 by letter SAI-SWT-0092 of 7/2/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. Sainco sent rev 1 by email of 9/12/03 and letter SAI-SWT-0156 of 9/11/03. Sainco sent rev 2 by letter SAI-SWT-0174 of 10/17/03 and email of 10/20/03. Telvent sent rev 3 by letter SAI-SWT-0208 of 1/14/04. Telvent sent rev 4 by letter SAI-SWT-0271 of 5/6/04. | JGG
|  | #REF! |  | Analyzers / Recorders Lists Unit 2 | 04360.MS039. 6-28005 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0304 of 10/6/04. | JBG
|  | #REF! |  | Electric Components Lists Unit 1 | 04360.MS039. 6-18006 | 1 | CC |  |  | 1 | 07/20/04 | 02/16/04 08/10/04 | SWT-SAI-0159 SWT-SAI-0225 |  |  | Telvent sent rev 0 by letter SAI-SWT-0191 of 11/26/03. Telvent sent rev 1 by letter SAI-SWT-0288 of 07/19/04. | JGG
|  | #REF! |  | Electric Components Lists Unit 2 | 04360.MS039. 6-28006 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0304 of 10/6/04. | JBG
|  | #REF! |  | PLC Lists Unit 1 | 04360.MS039. 6-18007 | 3 | CC |  | Telvent Unit 2 |  |  | 05/26/03 09/26/03 04/16/04 07/15/04 | SWT-SAI-0056 SWT-SAI-0100 SWT-SAI-0198 SWT-SAI-0218 |  |  | Sainco sent rev 0 by letter SAI-SWT-0041 of 4/29/03 and email of 4/30/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 2 by letter SAI-SWT-0250 of 03/15/04.Telvent sent rev 3 by letter SAI-SWT-0282 of 06/04/04. | JBG
|  | #REF! |  | PLC Lists Unit 2 | 04360.MS039. 6-28007 | 0 | PN |  | Telvent | [6 empty] | The document for Unit 1 is applicable also to the Unit 2 | GGT
|  | #REF! |  | Instruments List - Turbine Sampling System Unit 1 | 04360.MS039. 6-14001 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 1"
|  | #REF! |  | Instruments List - Turbine Sampling System Unit 2 | 04360.MS039. 6-24001 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 2"
|  | #REF! |  | Instruments List - Condensate Polishing Unit 1 | 04360.MS039. 6-14002 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 1"
|  | #REF! |  | Instruments List - Condensate Polishing Unit 2 | 04360.MS039. 6-24002 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 2"
|  | #REF! |  | Instruments List - Auxiliary Boiler Sampling Unit 1 | 04360.MS039. 6-14003 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 1"
|  | #REF! |  | Instruments List - Auxiliary Boiler Sampling Unit 2 | 04360.MS039. 6-24003 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 2"
|  | #REF! |  | Instruments List - Condenser System Unit 1 | 04360.MS039. 6-14004 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 1"
|  | #REF! |  | Instruments LIst - Condenser System Unit 2 | 04360.MS039. 6-24004 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Lists Unit 2"
|  | #REF! |  | Panels Data Sheets Unit 1 | 04360.MS039. 6-18101 | 1 | CC |  |  | 0 | 23/04/04 | 09/29/03 06/14/04 | SWT-SAI-0101 SWT-SAI-0216 |  |  | Sainco sent rev 0 by email of 8/1/03 and letter SAI-SWT-0125 on 07/28/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 1 by letter SAI-SWT-0271 of 5/6/04. | JGG
|  | #REF! |  | Panels Data Sheets Unit 2 | 04360.MS039. 6-28101 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04. | JBG
|  | #REF! |  | Instrumentation Data Sheets Unit 1 | 04360.MS039. 6-18102 | 4 | CC |  |  | 4 | 23/07/04 | 03/14/03 05/23/03 09/26/03 12/29/03 03/12/04 08/10/04 | SWT-SAI-0034 SWT-SAI-0055 SWT-SAI-0100 SWT-SAI-0145 SWT-SAI-0179 SWT-SAI-0225 |  |  | Sainco sent rev 0 by email of 2/12/03 and letter SAI-SWT-0019 of 2/17/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 2 by email and letter SAI-SWT-0182 of 14/11/03. Telvent sent rev 3 by letter SAI-SWT-0229 of 2/3/04. Telvent sent rev 4 by letter SAI-SWT-0288 of 07/19/04. | JGG
|  | #REF! |  | Instrumentation Data Sheets Unit 2 | 04360.MS039. 6-28102 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04. | JBG
|  | #REF! |  | Condenser Sampling Pumps Data Sheets Unit 1 | 04360.MS039. 6-18103 | 4 | CC |  |  | 3 | 23/04/04 | 10/01/03 12/22/03 03/12/04 04/29/04 10/05/04 | SWT-SAI-0120 SWT-SAI-0144 SWT-SAI-0179 SWT-SAI-0208 SWT-SAI-0236 |  |  | Sainco sent rev 0 by email of 8/4/03 and letter SAI-SWT-0126 of 07/29/03 (sent again on 8/6/03). Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0173 of 10/17/03 and email of 10/20/03. Telvent sent rev 2 by letter SAI-SWT-0233 of 2/12/04. Telvent sent rev 3 by letter SAI-SWT-0266 of 4/12/04. Telvent sent rev 4 by letter SAI-SWT-0291 of 7/22/04. | JGG
|  | #REF! |  | Condenser SamplingPumps Data Sheets Unit 2 | 04360.MS039. 6-28103 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04. | JBG
|  | #REF! |  | Secondary Sample Cooling Equipment Data Sheets Unit 1 | 04360.MS039. 6-18104 | 2 | CC |  |  | 1 | 23/04/04 | 08/21/03 03/12/04 05/12/04 | SWT-SAI-0091 SWT-SAI-0179 SWT-SAI-0210 |  |  | Sainco sent rev 0 by letter SAI-SWT-0092 of 7/2/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. Telvent sent rev 1 by letter SAI-SWT-0229 of 2/3/04. Telvent sent rev 2 by letter SAI-SWT-0270 of 4/28/04. | JBG
|  | #REF! |  | Secondary Sample Cooling Equipment Data Sheets Unit 2 | 04360.MS039. 6-28104 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04. | JBG
|  | #REF! |  | Analyzers / Recorders Data Sheets Unit 1 | 04360.MS039. 6-18105 | 4 | CC |  |  | 3 | 23/04/04 | 08/21/03 10/03/03 12/29/03 03/12/04 06/14/04 | SWT-SAI-0091 SWT-SAI-0121 SWT-SAI-0146 SWT-SAI-0179 SWT-SAI-0216 |  |  | Sainco sent rev 0 by letter SAI-SWT-0092 of 7/2/03. Sainco sent letter SAI-SWT-0142 on 08/11/03. Sainco sent rev 1 by email of 9/12/03 and letter SAI-SWT-0156 of 9/11/03. Sainco sent rev 2 by letter SAI-SWT-0174 of 10/17/03 and email of 10/20/03. Telvent sent rev 3 by letter SAI-SWT-0208 of 1/14/04. Telvent sent rev 4 by letter SAI-SWT-0271 of 5/6/04. | JBG
|  | #REF! |  | Analyzers / Recorders Data Sheets Unit 2 | 04360.MS039. 6-28105 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04. | JBG
|  | #REF! |  | Electric Components Data Sheets Unit 1 | 04360.MS039. 6-18106 | 1 | CC |  |  | 1 | 20/07/04 | 02/16/04 08/10/04 | SWT-SAI-0159 SWT-SAI-0225 |  |  | Telvent sent rev 0 by letter SAI-SWT-0191 of 11/26/03. Telvent sent rev 1 by letter SAI-SWT-0288 of 07/19/04. | JBG
|  | #REF! |  | Electric Components Data Sheets Unit 2 | 04360.MS039. 6-28106 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0306 of 10/07/04. | JBG
|  | #REF! |  | PLC Data Sheets Unit 1 | 04360.MS039. 6-18107 | 2 | CC |  |  |  |  | 05/26/03 09/26/03 04/16/04 | SWT-SAI-0056 SWT-SAI-0100 SWT-SAI-0198 |  |  | Sainco sent rev 0 by letter SAI-SWT-0041 of 4/29/03 and email of 4/30/03. Sainco sent rev 1 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Telvent sent rev 2 by letter SAI-SWT-0250 of 03/15/04 | JBG
|  | #REF! |  | PLC Data Sheets Unit 2 | 04360.MS039. 6-28107 | 0 | CC | [8 empty] | Telvent sent rev 0 by letter SAI-SWT-0304 of 10/6/04. | GGT
|  | #REF! |  | Cable and Terminal Blocks Specifications | 04360.MS039. 6-03100 | 0 | CC |  |  |  |  | 11/18/04 | SWT-SAI-0242 |  |  | Telvent sent rev 0 by letter SAI-SWT-0304 of 10/6/04. | JGG
|  | #REF! |  | Motor Data Sheets | 04360.MS039. 6-03100 |  | OR | [8 empty] | This information will be included in corresponding Data Sheet of each equipment.
|  | #REF! |  | Instruments Data Sheet - Turbine Sampling System Unit 1 | 04360.MS039. 6-14101 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 1"
|  | #REF! |  | Instruments Data Sheet - Turbine Sampling System Unit 2 | 04360.MS039. 6-24101 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 2"
|  | #REF! |  | Instruments Data Sheet - Condensate Polishing Unit 1 | 04360.MS039. 6-14102 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 1"
|  | #REF! |  | Instruments Data Sheet - Condensate Polishing Unit 2 | 04360.MS039. 6-24102 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 2"
|  | #REF! |  | Instruments Data Sheet - Auxiliary Boiler Sampling Unit 1 | 04360.MS039. 6-14103 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 1"
|  | #REF! |  | Instruments Data Sheet - Auxiliary Boiler Sampling Unit 2 | 04360.MS039. 6-24103 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 2"
|  | #REF! |  | Instruments Data Sheet - Condenser System Unit 1 | 04360.MS039. 6-14104 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 1"
|  | #REF! |  | Instruments Date Sheet - Condenser System Unit 2 | 04360.MS039. 6-24104 |  | OR | [8 empty] | Replaced by "Equipment and Instrument Data Sheets Unit 2"
|  | #REF! |  | PLC Program - Turbine Sampling System Unit 1 | 04360.MS039. 6-14201 | 0 | PN | 2003-05-30 | Telvent | [7 empty] | JBG
|  | #REF! |  | PLC Program - Turbine Sampling System Unit 2 | 04360.MS039. 6-24201 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Program - Condensate Polishing Unit 1 | 04360.MS039. 6-14202 | 0 | PN | 2003-05-30 | Telvent | [7 empty] | JBG
|  | #REF! |  | PLC Program - Condensate Polishing Unit 2 | 04360.MS039. 6-24202 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Program - Auxiliary Boiler Sampling Unit 1 | 04360.MS039. 6-14203 | 0 | PN | 2003-05-30 | Telvent | [7 empty] | JBG
|  | #REF! |  | PLC Program - Auxiliary Boiler Sampling Unit 2 | 04360.MS039. 6-24203 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC Program - Condenser System Unit 1 | 04360.MS039. 6-14204 | 0 | PN | 2003-05-30 | Telvent | [7 empty] | JBG
|  | #REF! |  | PLC Program - Condenser System Unit 2 | 04360.MS039. 6-24204 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC I/O List- Turbine Sampling System Unit 1 | 04360.MS039. 6-14301 | 3 | RE | 07/29/04 | Telvent |  |  | 09/26/03 01/30/04 04/16/04 07/15/04 | SWT-SAI-0100 SWT-SAI-0153 SWT-SAI-0198 SWT-SAI-0218 |  |  | Sainco sent rev 0 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0205 of 12/29/03. Telvent sent rev 2 by letter SAI-SWT-0250 of 03/15/04.Telvent sent rev 3 by letter SAI-SWT-0282 of 06/04/04 | JBG
|  | #REF! |  | PLC I/O List - Turbine Sampling System Unit 2 | 04360.MS039. 6-24301 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC I/O List - Condensate Polishing Unit 1 | 04360.MS039. 6-14302 | 3 | RE | 07/29/04 | Telvent |  |  | 09/26/03 01/30/04 04/16/04 07/15/04 | SWT-SAI-0100 SWT-SAI-0153 SWT-SAI-0198 SWT-SAI-0218 |  |  | Sainco sent rev 0 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0205 of 12/29/03. Telvent sent rev 2 by letter SAI-SWT-0250 of 03/15/04.Telvent sent rev 3 by letter SAI-SWT-0282 of 06/04/04 | JBG
|  | #REF! |  | PLC I/O List - Condensate Polishing Unit 2 | 04360.MS039. 6-24302 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC I/O List - Auxiliary Boiler Sampling Unit 1 | 04360.MS039. 6-14303 | 3 | RE | 07/29/04 | Telvent |  |  | 09/26/03 01/30/04 04/16/04 07/15/04 | SWT-SAI-0100 SWT-SAI-0153 SWT-SAI-0198 SWT-SAI-0218 |  |  | Sainco sent rev 0 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0205 of 12/29/03. Telvent sent rev 2 by letter SAI-SWT-0250 of 03/15/04.Telvent sent rev 3 by letter SAI-SWT-0282 of 06/04/04 | JBG
|  | #REF! |  | PLC I/O List - Auxiliary Boiler Sampling Unit 2 | 04360.MS039. 6-24303 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | PLC I/O List - Condenser System Unit 1 | 04360.MS039. 6-14304 | 3 | RE | 07/29/04 | Telvent |  |  | 09/26/03 01/30/04 04/16/04 07/15/04 | SWT-SAI-0100 SWT-SAI-0153 SWT-SAI-0198 SWT-SAI-0218 |  |  | Sainco sent rev 0 by letter SAI-SWT-0099 of 7/14/03. Sainco sent letter SAI-SWT-0155 of 9/11/03. Sainco sent rev 1 by letter SAI-SWT-0205 of 12/29/03. Telvent sent rev 2 by letter SAI-SWT-0250 of 03/15/04.Telvent sent rev 3 by letter SAI-SWT-0282 of 06/04/04 | JBG
|  | #REF! |  | PLC I/O LIst - Condenser System Unit 2 | 04360.MS039. 6-24304 | 0 | PN | Approval Unit 1 | Telvent
|  | #REF! |  | MMI Graphic Display and Description of Operation Unit 1 and Unit 2 | 04360.MS039. 6-04401 | 0 | RE | 2004-11-26 | TPC | [6 empty] | Telvent sent rev 0 by letter SAI-SWT-0324 of 11/12/04 | JBG
|  | #REF! |  | MMI Graphic Display Unit 2 | 04360.MS039. 6-24401 |  | OR | [8 empty] | Included in document 04360.MS039. 6-04401 | JBG
|  | #REF! |  | MMI Descripcion of Operation Unit 1 | 04360.MS039. 6-14501 |  | OR | [8 empty] | Included in document 04360.MS039. 6-04401 | JBG
|  | #REF! |  | MMI Descripcion of Operation Unit 2 | 04360.MS039. 6-24501 |  | OR | [8 empty] | Included in document 04360.MS039. 6-04401 | JBG
|  | #REF! |  | Statistical Process Control Manual | 04360.MS039. 6-04600 | 0 | PN | 2004-11-30 | Telvent | [7 empty] | JBG
|  | #REF! |  | Catalog Information List | 04360.MS039. 6-08100 | 0 | PN | 2003-05-16 | Telvent | [7 empty] | JBG
|  | #REF! |  | Bill of Materials - Electrical and Instrumentation | 04360.MS039. 6-08200 |  | OR | [8 empty] | Replaced by document "Equipment and Instrument Lists Unit 1 and Unit 2"
#REF!
|  | #REF! |  | Data Link Design Input | 04360.MS039. 6-04010 | 2 | CC |  | Telvent |  |  | 2/20/03 4/07/03 5/21/03 | SWT-SAI-0028 SWT-SAI-0041 SWT-SAI-0054 |  |  | Sainco sent rev 0 by email of 12/12/02 and letter SAI-SWT-0015 of 1/27/03. Sainco sent rev 1 by email of 20/3/03 and letter SAI-SWT-0028 of 19/3/03. Sainco sent rev 2 by letter SAI-SWT-0033 of 04/10/03 and email of 04/11/03 | JBG
|  | #REF! |  | Data Link Format Database Unit 1 | 04360.MS039. 6-14010 | 1 | CC |  | Telvent |  |  | 2/20/03 4/07/03 | SWT-SAI-0028 SWT-SAI-0041 |  |  | Sainco sent rev 0 by email of 12/12/02 and letter SAI-SWT-0015 of 1/27/03. Sainco sent rev 1 by email of 20/3/03 and letter SAI-SWT-0028 of 19/3/03. | JBG
|  | #REF! |  | Data Link Format Database Unit 2 | 04360.MS039. 6-24010 | 0 | PN | Approval Unit 1 | Telvent | [7 empty] | GGT
|  | #REF! |  | I/O List Interface Database Unit 1 | 04360.MS039. 6-14012 | 0 | CC |  |  |  |  | 2/20/2003 | SWT-SAI-0028 |  |  | Sainco sent rev 0 by email of 12/12/02 and letter SAI-SWT-0015 of 1/27/03. | JBG
|  | #REF! |  | I/O List Interface Database Unit 2 | 04360.MS039. 6-24012 | 0 | PN | Approval Unit 1 | Telvent | [7 empty] | GGT
|  | #REF! |  | Control Logic Interface Unit 1 | N/A |  | OR | [8 empty] | There is no need of such document given that no control actions will be perfomed from the RMU system | GGT
|  | #REF! |  | Control Logic Interface Unit 2 | N/A |  | OR | [8 empty] | There is no need of such document given that no control actions will be perfomed from the RMU system | GGT
|  | #REF! |  | Instrument installation details with bill of materials | N/A |  | OR | [8 empty] | These details will be included in the "Equipment Layout Drawings"
|  | #REF! |  | Instrument location drawings/plans | N/A |  | OR | [8 empty] | These details will be included in the "Equipment Layout Drawings"
#REF!
|  | #REF! |  | 5. Test and Inspection
|  | #REF! |  | Inspection/Test Reports | 04360.MS039. 4-08101 | 0 | PN |  | Telvent | [6 empty] | To be submitted to TPC upon completion of the tests
|  | #REF! |  | Manufacturing and Inspection Plan -Remote Sampling Cooling Panels of Turbine Sampling System | 04360.MS039. 4-08201 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Cooling and Analysis Panel of Turbine Sampling System | 04360.MS039. 4-08202 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Panel with Secundary Sampling Cooling of Turbine Sampling System. | 04360.MS039. 4-08203 |  | OR | [8 empty] | This panel is not existing (included in other panels) | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Control and Recorder Panel of Turbine Sampling System. | 04360.MS039. 4-08204 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Chiller Equipment Panel of Turbine Sampling System | 04360.MS039. 4-08205 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Cooling and Analysis Panel of Condensate Polishing Sampling System. | 04360.MS039. 4-08302 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Panel with Secundary Sampling Cooling of Condensate Polishing. | 04360.MS039. 4-08303 |  | OR | [8 empty] | This panel is not existing (included in other panels) | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Control & Recorder Panel of Condensate Polishing.Sampling System. | 04360.MS039. 4-08304 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Chiller Equipment Panel of Condensate Polishing Sampling System. | 04360.MS039. 4-08305 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Cooling and Analysis Panel of Auxiliary Boiler Sampling System. | 04360.MS039. 4-08402 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Panel with Secundary Sampling Cooling of Auxiliary Boiler Sampling System. | 04360.MS039. 4-08403 |  | OR | [8 empty] | This panel is not existing (included in other panels) | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Control & Recorder Panel of Auxiliary Boiler Sampling System. | 04360.MS039. 4-08404 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling and Analysis Panel of Condenser Sampling System. | 04360.MS039. 4-08502 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Sampling Panel with Secundary Sampling Cooling of Condenser System. | 04360.MS039. 4-08503 |  | OR | [8 empty] | This panel is not existing (included in other panels) | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan - Control & Recorder Panel of Condenser Sampling System. | 04360.MS039. 4-08504 |  | OR | [8 empty] | This document is replaced by other specific documents for different manufacturing stages | JBG/JCL
|  | #REF! |  | Inspection and Test Plan - Panel Structural Manufacturing, Equipment Integration in the Panels, FAT, Packing and Shipping | 04360.MS039. 4-08001 | 4 | CC |  |  | 1 3 | 23/04/04 08/09/04 | 6/18/03 9/4/03 9/9/03 07/19/04 09/29/04 10/21/04 | SWT-SAI-0071 SWT-SAI-0093 SWT-SAI-0094 SWT-SAI-0221 SWT-SAI-0234 SWT-SAI-0238 |  |  | Sainco sent rev 0 by email of 05/29/03 and letter SAI-SWT-0076 of 6/6/03. Sainco sent rev 1 by email of 08/13/03 and letter SAI-SWT-0145 of 8/12/03. Telvent sent rev 2 by letter SAI-SWT-0285 of 07/05/04. Telvent sent rev 3 by letter SAI-SWT-0298 of 09/08/04. Telvent sent rev 4 by letter SAI-SWT-0305 of 10/06/04. | JBG/JCL
|  | #REF! |  | Manufacturing and Inspection Plan – Equipment Integration in the Panels | 04360.MS039. 4-08002 |  | OR |  | Telvent | [6 empty] | This document is replaced by document 04360.MS039. 4-08001 | JBG
|  | #REF! |  | Test and Inspection Plan – FAT, Packing and Shipping | 04360.MS039. 4-08003 |  | OR |  | Telvent | [6 empty] | This document is replaced by document 04360.MS039. 4-08001. Document "04360.MS039. 4-08003 rev 0" submitted by letter SAI-SWT-MS039-0282 of 06/04/04 shall be disregarded. | JBG
#REF!
|  | #REF! |  | Factory Acceptance Test Procedures - RSCS Panel of Turbine Sampling System | 04360.MS039. 4-18100 | 0 | CC |  |  |  |  | 8/10/04 | SWT-SAI-0225 |  |  | Telvent sent rev 0 by letter SAI-SWT-0287 of 07/15/04. | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - RSCS Panel of Turbine Sampling System Unit 2 | 04360.MS039. 4-28100 | 0 | OR | [8 empty] | The FAT procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - Analyzer Panels | 04360.MS039. 4-18101 | 0 | CC |  |  |  |  | 8/10/04 | SWT-SAI-0225 |  |  | Telvent sent rev 0 by letter SAI-SWT-0287 of 07/15/04. | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - Analyzer Panels Unit 2 | 04360.MS039. 4-28101 | 0 | OR | [8 empty] | The FAT procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - Sample Conditioning Panels and Chiller Panels | 04360.MS039. 4-18102 | 0 | PN | 2004-11-12 | Telvent | [7 empty] | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - Sample Conditioning Panels and Chiller Panels Unit 2 | 04360.MS039. 4-28102 | 0 | OR | [8 empty] | The FAT procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - Control & Recorder Panels | 04360.MS039. 4-18103 | 0 | PN | 2004-11-12 | Telvent | [7 empty] | JBG
|  | #REF! |  | Factory Acceptance Test Procedures - Control & Recorder Panels Unit 2 | 04360.MS039. 4-28103 | 0 | OR | [8 empty] | The FAT procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! | [14 empty] | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Turbine Sampling System | 04360.MS039. 4-18200 | 0 | PN | 2004-12-07 | Telvent | [6 empty] | Pending confirmation by TPC/S&W date of Performance Tests | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Turbine Sampling System Unit 2 | 04360.MS039. 4-28200 | 0 | PN | 2003-10-03 | Telvent | [6 empty] | The Final Acceptance Test Procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Condensate Polishing Sampling System | 04360.MS039. 4-18201 | 0 | PN | 2004-12-07 | Telvent | [6 empty] | Pending confirmation by TPC/S&W date of Performance Tests | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Condensate Polishing Sampling System Unit 2 | 04360.MS039. 4-28201 | 0 | PN | 2003-10-03 | Telvent | [6 empty] | The Final Acceptance Test Procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Auxiliary Boiler Sampling System | 04360.MS039. 4-18202 | 0 | PN | 2004-12-07 | Telvent | [6 empty] | Pending confirmation by TPC/S&W date of Performance Tests | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Auxiliary Boiler Sampling System Unit 2 | 04360.MS039. 4-28202 | 0 | PN | 2003-10-03 | Telvent | [6 empty] | The Final Acceptance Test Procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Condenser Sampling System | 04360.MS039. 4-18203 | 0 | PN | 2004-12-07 | Telvent | [6 empty] | Pending confirmation by TPC/S&W date of Performance Tests | JBG
|  | #REF! |  | Final Acceptance Test Procedures - Condenser Sampling System Unit 2 | 04360.MS039. 4-28203 | 0 | PN | 2003-10-03 | Telvent | [6 empty] | The Final Acceptance Test Procedures are applicable to both the Unit 1 and the Unit 2 | JBG
|  | #REF! |  | Performance Test Procedures |  |  | OR | [8 empty] | Included in Factory and Final Acceptance Test Procedures
#REF!
|  | #REF! |  | Hydrostatic Test Procedure | 04360.MS039 .4-02001 | 1 | CC | 2004-11-12 | Telvent |  |  | 05/03/04 06/14/04 | SWT-SAI-0209 SWT-SAI-0216 |  |  | Telvent sent rev 0 by letter SAI-SWT-0253 of 3/19/04. Telvent sent rev 1 by letter SAI-SWT-0271 of 5/6/04.
|  | #REF! |  | Liquid Sample Functional Test | 04360.MS039 .4-02002 |  | OR | [8 empty] | This document to be included in FAT or SAT documents
|  | #REF! |  | Dielectrical Strength Test Procedure | º |  | OR | [8 empty] | This document to be included in FAT or SAT documents
|  | #REF! |  | Electrical Point to Point Test | 04360.MS039 .4-03002 |  | OR | [8 empty] | This document to be included in FAT or SAT documents
|  | #REF! |  | Test Procedure for the Isothermal Bath Recirculation Pumps for Lungmen Units 1 & 2 | 04360.MS039 .4-08300 | 0 | CC |  |  |  |  | 2004-08-19 | SWT-SAI-0228 |  |  | Telvent sent rev 0 by letter SAI-SWT-0294 of 8/05/04.
|  | #REF! |  | Test Procedure for the Condenser Sampling Pumps for Lungmen Units 1 & 2 | 04360.MS039 .4-08301 | 0 | CC |  |  |  |  | 2004-08-19 | SWT-SAI-0228 |  |  | Telvent sent rev 0 by letter SAI-SWT-0294 of 8/05/04.
|  | #REF! |  | Shop Inpection and Test Report for Remote Sampling Cooler Panels and Analyzer Panels for Units 1 and 2 | 04360.MS039 .4-08400 | 0 | CC |  |  |  |  | 10/22/04 | SWT-SAI-0239 |  |  | Telvent sent rev 0 by letter SAI-SWT-0317 of 10/20/04.
|  | #REF! |  | Shop Inpection and Test Report for Sample Conditioning Racks, Chiller Equipment Panels and Control and Recorder Panels Unit 1 | 04360.MS039 .4-08401 | 0 | PN | final panel | Telvent
|  | #REF! |  | Shop Inpection and Test Report for Sample Conditioning Racks, Chiller Equipment Panels and Control and Recorder Panels Unit 2 | 04360.MS039 .4-08402 | 0 | PN |  | Telvent
|  | #REF! |  | 6. Transportation and Installation
|  | #REF! |  | Special Transportation Considerations | 04360.MS039. 7-08001 | 0 | OR | 2003-05-30 | Telvent | [6 empty] | This matter is included in the document "Packing Procedures, Special Transportation Considerations and Special Storage Requirements" | JBG
|  | #REF! |  | Erection and Assembly Instructions |  |  | OR | [8 empty] | Included in the Installation Instructions
|  | #REF! |  | Installation Manuals |  |  | OR | [8 empty] | Included in the Installation Instructions
|  | #REF! |  | Installation Instructions for Turbine Sampling System | 04360.MS039. 7-08110 | 0 | PN | 2004-11-30 | Telvent | [7 empty] | JBG
|  | #REF! |  | Installation Instructions for Condensate Polishing Sampling System | 04360.MS039. 7-08120 | 0 | PN | 2004-11-30 | Telvent
|  | #REF! |  | Installation Instructions for Auxiliary Boiler Sampling System | 04360.MS039. 7-08130 | 0 | PN | 2004-11-30 | Telvent
|  | #REF! |  | Installation Instructions for Condenser Sampling System | 04360.MS039. 7-08140 | 0 | PN | 2004-11-30 | Telvent
|  | #REF! |  | Packing Procedures, Special Transportation Considerations and Special Storage Requirements | 04360.MS039. 7-08002 | 1 | CC |  |  |  |  | 12/11/03 04/13/04 | SWT-SAI-0141 SWT-SAI-0197 |  |  | Sainco sent rev 0 by email and letter SAI-SWT-0181 of 13/11/03. Telvent sent rev 1 by letter SAI-SWT-0262 of 03/30/04 | JBG
#REF!
#REF!
|  | #REF! |  | 7. Operation and Maintenance
|  | #REF! |  | Operation and Maintenance Manual for Turbine Sampling System | 04360.MS039. 7-08310 | 0 | PN | 2004-11-12 | Telvent | [7 empty] | JBG
|  | #REF! |  | Operation and Maintenance Manual for Condensate Polishing Sampling System | 04360.MS039. 7-08320 | 0 | PN | 2004-11-19 | Telvent
|  | #REF! |  | Operation and Maintenance Manual for Auxiliary Boiler Sampling System | 04360.MS039. 7-08330 | 0 | PN | 2004-11-19 | Telvent
|  | #REF! |  | Operation and Maintenance Manual for Condenser Sampling System | 04360.MS039. 7-08340 | 0 | PN | 2004-11-19 | Telvent
#REF!
|  | #REF! |  | Maintenance Manual for Turbine Sampling System | 04360.MS039. 7-08410 |  | OR | [8 empty] | This matter is included in the corresponding Operation and Maintenance Manual | JBG
|  | #REF! |  | Maintenance Manual for Condensate Polishing Sampling System | 04360.MS039. 7-08420 |  | OR | [8 empty] | This matter is included in the corresponding Operation and Maintenance Manual
|  | #REF! |  | Maintenance Manual for Auxiliary Boiler Sampling System | 04360.MS039. 7-08430 |  | OR | [8 empty] | This matter is included in the corresponding Operation and Maintenance Manual
|  | #REF! |  | Maintenance Manual for Condenser Sampling System | 04360.MS039. 7-08440 |  | OR | [8 empty] | This matter is included in the corresponding Operation and Maintenance Manual
#REF!
|  | #REF! |  | Special storage requirements | 04360.MS039. 7-08500 |  | OR | [8 empty] | This matter is included in document "Packing Procedures, Special Transportation Considerations and Special Storage Requirements" | JBG
|  | #REF! |  | Spare parts listing | 04360.MS039. 6-08300 | 0 | PN | 2004-11-08 | Telvent | [7 empty] | JBG
|  | #REF! |  | Special tools listing | 04360.MS039. 6-08400 |  | OR | [8 empty] | Not necessary special tools for the installation | JBG
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
|  | #REF! |  | STATUS :
|  | #REF! |  | PN = Planed
|  | #REF! |  | RE = Revision
|  | #REF! |  | CC = Completed/Closed (approved for the Unit 1 or the Unit 2)
|  | #REF! |  | CC2 = Completed/Closed (approved for both the Unit 1 and the Unit 2)
|  | #REF! |  | OR = Outdated/Replaced
Note on F293: SEJSGG: la rev 0 de los PLC Internal Wiring y PLC/PC/LAN Wiring eran ref. 03010, 03110, etc..... Pendientes de Rev. 1 a Maribel.
Note on F295: SEJSGG: la rev 0 de los PLC Internal Wiring y PLC/PC/LAN Wiring eran ref. 03010, 03110, etc..... Pendientes de Rev. 1 a Maribel.
Note on F299: SEJSGG: la rev 0 de los PLC Internal Wiring y PLC/PC/LAN Wiring eran ref. 03010, 03110, etc..... Pendientes de Rev. 1 a Maribel.
Note on J334: SEJSGG: Poner nota "THIS DRAWING IS TYPICAL FOR UNIT 2"
Note on J335: SEJSGG: Poner nota "THIS DRAWING IS TYPICAL FOR UNIT 2"
Note on J424: SEJSGG: actualizar